## CW52
Reporting Part |  |  |  | None Reporting Part
2025-12-23 | CW52
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Trip from HQ | * Kim, WonTae ¦ Annual Leave: 11/17~11/18. Sick Leave 11/19~12/02 due to Backache / Extend Sick Leave 12/03~12/18
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Remaining items for Sign-off : Apps : - SW 5.6.0 upgrade : End of Jan 2026 - RS4 contamination test : 12nd Dec ~ TBD Service : - GunPM : Jan 2026 - Particle cleaning : 17th Dec - EFEM interlock installation : TBD. * Target for Sign-off : end of Jan 2026. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026 2) RS4 bottle installation - Target Completion : end of 2025.
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
|  | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Priod : April ~ June, it need to be fixed by Samsung and ZEISS. - Items : EUV binary etch (TBD) 2. Delta Coulmn Performance Evaluation * Metrix need to be discussed with Samsung and ZEISS.
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document.
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Improvement of selectivity up to 300% with new gas chemistry * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement. 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Need S/W upgrade FF2 (4.1.0) Full Feature * Task: S/W upgrade. (12/16 ~ 12/17) * Action: FF2 CR on Dec 15th , smoke tests, patch notes, and action items will be shared with SSC. * Result: FF2 Favor upgrade completed, connection confirmed by customer’s PC All smoke test items passed
| AAA EUV (AIMS EUV3.0) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Obtain Lincese file + Configuration clarification * Action: Credential error occurred. Plan to have HQ call and supprot (CW51 ~ ) * Result: N/A
| AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Customer shared the EUVR data (December 17th) * Plan: HQ prepare the report
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 * Task : Job creation automation preparation * Action: Have internal alignment call on December 16th * Plan: HQ will share relevant document to SSC (December 25th)
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS shared some idea to test for camera meter and interferometer on blank 1&2 * Plan: Have customer feedback on ZEISS suggestion (December 23rd)
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: HQ prepare slides that what will be implemented in next FTM version and share it to customer +Follow up on the items that discussed with Samsung for job automation (FTM modification scheduled to be released by 2026 April)
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (open in CW51 2025) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Check network status between Tool PC and FAVOR, some action items from HQ (restart FTM service, open port etc) *Plan: HQ think about if it is related to updated FTM version 4.0.0 itself
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: HQ shared fine tune result for phase 1 + Have a meeting with Samsung for upgrade concept (December 5th) +Samsung provide Case B mask (December 5th) * Plan: Plan to have a additional meeting with Samsung with HQ feedback
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| PROVE | neXT (SR1) (DongHoon, Koo) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action:Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Further discussion about planning of Action item will take place on next PROVE application call * Plan: Internal alignment between HQ and Local team to provide FAVOR SW fix to the customer
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Await further measurement from Samsung to analyze.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: Evaluation of TTTM signature on PROVE neXT * Task: Customer will measure Same grid mask that is used for IPRO tool TTTM at PROVE next without TTTM calibration file. * Action: Compare the result with IPRO to check the signature of IPRO on PROVE tool. * Result: Still waiting for the measurement from the customer * Plan: Discuss further in next TTTM session with SAMSUNG
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Under development | * TTTM on site meeting in 23rd Sep - SEC plan to make an appropriate mask and keep working - Completed. * Workshop schedule: 25th Sep. - Completed 4 HQ visited.
| Repair | LE #1(M79) | 1. M79 ATP Pending items * Priority : Low * Situation : Remaining Pending items. * Task / Action plan. a. DUV Edge profile improvement - Customer will confirm on end of 2025. - Target Completion : end of 2025
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> SKH commitment about AR purchasing is required for developing AR item #2 and #7 - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation (w/o SimOp) - Target Completion : With SimOp Demo is targeted to start on Jan 2026 * Result : - SimOp installtion for neXT&LE will be completed on end of Dec. * Plan : - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : TBD * Agenda : a. [M79] Over etch - some part EPD cluster don't close b. [M44] MeRiT_M44_Pattern copy fail of Fine mode ---> Ticket is closed c. [M26] [M44]_DC Mark Size & Scanning ---> Ticket is closed d. [M44] Abnormal EPD ---> Ticket is closed e. [M44] EUV PSM etching - Corner ---> Ticket is closed f. [M44] EUV PSM_Set up the Slope EPD in SKH ---> Ticket is closed
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho)
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Installation support: NTT technician scheduled for February 2026 2) under Alignment with NTT Local * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59/ 61) - Action: Issue tracing in progress - Recovery attempt: Scheduled for Thursday
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA Matlab runtime error occurring for over 5 defect sites analysis (12/08) * Task : To give POA for current issue. * Action: Suggested to deleted cache folders (C:\FAVOR\AIMS AutoAnalysis\Matlab\McrCache) 1) (Resolved by re-installing AAA server s/w by customer on 15th Dec. * Result: Deleting cache folders does not work for this issue, deeper investigation required with HQ. 1) Result: OK. (15th Dec) - Temporary solution: reinstall AAA  can proceed 10+ defect site analysis
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AAA (ByungWan) | * Situation: AIMS 1x (2nd) S09 shown abnormal hole pattern (12/02) * Task: find out root cause * Action: Measured with CAA mask and shared to HQ. (Suspect Vibration) 1) H/W plan to visit and follow up POA2 provided HQ. and suspect NA Motor may have an issue on 16th Dec * Result: (HW: Action taken: CW51. Resolved)
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task : AIMS 1x CD delta matching * Action: HQ propose to measure new PDM mask and investigate it * Result: All type of defect were measured. Measure data was shared on 10.10 to HQ * Plan: HQ evaluation is on-going. [CW44]
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: HQ conduct simulation and share the report (December 17th) * Plan: Perform the process on the customer mask | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Result: Await until the customer provide clip file. * Plan: After receiving the clip file, we will forward it to HQ and continue the demo evaluation.
| PROVE | High Resolution (Dev) | * Workshop schedule: 24th Sep. * Pitch defining ZEISS and customer table will be shared by this week for internal (CW46) by HyeRim
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP Schedule by End of Jan 1) Target Completion : 9th Jan 2026 2) ATP On going : 10th Nov ~ in Progress * ATP schedule has been delayed due to mask noise issue on AIMS measurement.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Failure of customer mask (40% of production volume) - AIMS Fab Neo F-ATP * Task : Need to adjust optic beam path * Action: HQ H/W Engineer plan to dispatch in CW04(plan) * Result: N/A * Plan: fATP sign off once mask alingnment done with customer mask (CW05)

## CW01
Reporting Part |  |  |  | None Reporting Part
2025-12-30 | CW01
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Remaining items for Sign-off : Apps : - SW 5.6.0 upgrade : End of Jan 2026 - RS4 contamination test : 12nd Dec ~ TBD Service : - GunPM : Jan 2026 - Particle cleaning : 17th Dec - EFEM interlock installation : TBD. * Target for Sign-off : end of Jan 2026. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026 2) RS4 bottle installation - Target Completion : end of 2025.
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
|  | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Priod : April ~ June, it need to be fixed by Samsung and ZEISS. - Items : Delta column evaluation and PT based EUV PSM evaluation on LE tool --> HQ need to confirm suggsted items. 2. Delta Coulmn Performance Evaluation * 24th Dec. Samsung has provided feedback to ZEISS for evaluation items
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document.
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Improvement of selectivity up to 300% with new gas chemistry * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement. 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q1 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Waiting feedback from HQ.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Customer shared the EUVR data (December 17th) * Plan: HQ prepare the report
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 * Task : Job creation automation preparation * Action: Have internal alignment call on December 16th * Plan: HQ will share relevant document to SSC (December 25th)
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS shared some idea to test for camera meter and interferometer on blank 1&2 * Plan: Have customer feedback on ZEISS suggestion (December 23rd)
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: HQ prepare slides that what will be implemented in next FTM version and share it to customer +Follow up on the items that discussed with Samsung for job automation (FTM modification scheduled to be released by 2026 April)
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (open in CW51 2025) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Check network status between Tool PC and FAVOR, some action items from HQ (restart FTM service, open port etc) *Plan: HQ think about if it is related to updated FTM version 4.0.0 itself
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: HQ shared fine tune result for phase 1 + Have a meeting with Samsung for upgrade concept (December 5th) +Samsung provide Case B mask (December 5th) * Plan: Plan to have a additional meeting with Samsung with HQ feedback
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| PROVE | neXT (SR1) (DongHoon, Koo) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action:Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Further discussion about planning of Action item will take place on next PROVE application call * Plan: Internal alignment between HQ and Local team to provide FAVOR SW fix to the customer
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Await further measurement from Samsung to analyze.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: Evaluation of TTTM signature on PROVE neXT * Task: Customer will measure Same grid mask that is used for IPRO tool TTTM at PROVE next without TTTM calibration file. * Action: Compare the result with IPRO to check the signature of IPRO on PROVE tool. * Result: Still waiting for the measurement from the customer * Plan: Discuss further in next TTTM session with SAMSUNG
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Under development | * TTTM on site meeting in 23rd Sep - SEC plan to make an appropriate mask and keep working - Completed. * Workshop schedule: 25th Sep. - Completed 4 HQ visited.
| Repair | LE #1(M79) | 1. M79 ATP Pending items * Priority : Low * Situation : Remaining Pending items. * Task / Action plan. a. DUV Edge profile improvement - Customer will confirm on end of 2025. - Target Completion : end of 2025
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> SKH commitment about AR purchasing is required for developing AR item #2 and #7 - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of March 2026 - SimOp installtion for neXT&LE will be completed on end of Jan 2026 * Plan : - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : TBD * Agenda : a. [M79] Over etch - some part EPD cluster don't close b. [M44] MeRiT_M44_Pattern copy fail of Fine mode ---> Ticket is closed c. [M26] [M44]_DC Mark Size & Scanning ---> Ticket is closed d. [M44] Abnormal EPD ---> Ticket is closed e. [M44] EUV PSM etching - Corner ---> Ticket is closed f. [M44] EUV PSM_Set up the Slope EPD in SKH ---> Ticket is closed
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59/ 61) - Action: Issue tracing in progress - Recovery attempt: Scheduled for Thursday
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA Matlab runtime error occurring for over 5 defect sites analysis (12/08) * Task : To give POA for current issue. * Action: Suggested to deleted cache folders (C:\FAVOR\AIMS AutoAnalysis\Matlab\McrCache) 1) (Resolved by re-installing AAA server s/w by customer on 15th Dec. * Result: Deleting cache folders does not work for this issue, deeper investigation required with HQ. 1) Result: OK. (15th Dec) - Temporary solution: reinstall AAA  can proceed 10+ defect site analysis
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AAA (ByungWan) | * Situation: AIMS 1x (2nd) S09 shown abnormal hole pattern (12/02) * Task: find out root cause * Action: Measured with CAA mask and shared to HQ. (Suspect Vibration) 1) H/W plan to visit and follow up POA2 provided HQ. and suspect NA Motor may have an issue on 16th Dec * Result: (HW: Action taken: CW51. Resolved)
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task : AIMS 1x CD delta matching * Action: HQ propose to measure new PDM mask and investigate it * Result: All type of defect were measured. Measure data was shared on 10.10 to HQ * Plan: HQ evaluation is on-going. [CW44]
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: HQ conduct simulation and share the report (December 17th) * Plan: Perform the process on the customer mask | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | High Resolution (Dev) | * Workshop schedule: 24th Sep. * Pitch defining ZEISS and customer table will be shared by this week for internal (CW46) by HyeRim
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP Schedule by End of Jan 1) Target Completion : 9th Jan 2026 2) ATP On going : 10th Nov ~ in Progress * ATP schedule has been delayed due to mask noise issue on AIMS measurement --> ATP will be perforemd with mask noise spec. but SSC will provide additional support after complete ATP for find tuning including mask noise.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Failure of customer mask (40% of production volume) - AIMS Fab Neo F-ATP * Task : Need to adjust optic beam path * Action: HQ H/W Engineer plan to dispatch in CW04(plan) * Result: N/A * Plan: fATP sign off once mask alingnment done with customer mask (CW05)
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD

## CW02
Reporting Part |  |  |  | None Reporting Part
2026-01-06 | CW02
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Remaining items for Sign-off : Apps : - SW 5.6.0 upgrade : End of Jan 2026 - RS4 contamination test : 12nd Dec ~ TBD Service : - GunPM : Jan 2026 - Particle cleaning : 17th Dec - EFEM interlock installation : TBD. * Target for Sign-off : end of Jan 2026. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026 2) RS4 bottle installation - Target Completion : end of 2025.
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
|  | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Priod : April ~ June, it need to be fixed by Samsung and ZEISS. - Items : Delta column evaluation and PT based EUV PSM evaluation on LE tool --> HQ need to confirm suggsted items. 2. Delta Coulmn Performance Evaluation * 24th Dec. Samsung has provided feedback to ZEISS for evaluation items
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document.
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Improvement of selectivity up to 300% with new gas chemistry * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement. 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q1 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Waiting feedback from HQ.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Customer shared the EUVR data (December 17th) * Plan: HQ prepare the report
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 * Task : Job creation automation preparation * Action: Share first version of automation document to customer * Plan: Have updated file to customer on Jan 19th and have a call on Jan 20th
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS shared some idea to test for camera meter and interferometer on blank 1&2 * Plan: Have customer feedback on ZEISS suggestion (Delayed  Samsung would like to have blank 8 report before share the feedback)
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: HQ prepare slides that what will be implemented in next FTM version and share it to customer +Follow up on the items that discussed with Samsung for job automation (FTM modification scheduled to be released by 2026 April)
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (open in CW51 2025) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Check network status between Tool PC and FAVOR, some action items from HQ (restart FTM service, open port etc) *Plan: HQ think about if it is related to updated FTM version 4.0.0 itself
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Had a customer meeting on 23rd Dec. Received further request (Gantt chart) * Plan: ZEISS prepare gantt chart including to process blank A & B (due date : January 9th)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| PROVE | neXT (SR1) (DongHoon, Koo) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action:Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Further discussion about planning of Action item will take place on next PROVE application call * Plan: Internal alignment between HQ and Local team to provide FAVOR SW fix to the customer
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Await further measurement from Samsung to analyze.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: Evaluation of TTTM signature on PROVE neXT * Task: Customer will measure Same grid mask that is used for IPRO tool TTTM at PROVE next without TTTM calibration file. * Action: Compare the result with IPRO to check the signature of IPRO on PROVE tool. * Result: Still waiting for the measurement from the customer * Plan: Discuss further in next TTTM session with SAMSUNG
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Under development | * TTTM on site meeting in 23rd Sep - SEC plan to make an appropriate mask and keep working - Completed. * Workshop schedule: 25th Sep. - Completed 4 HQ visited.
| Repair | LE #1(M79) | 1. M79 ATP Pending items * Priority : Low * Situation : Remaining Pending items. * Task / Action plan. a. DUV Edge profile improvement - Customer will confirm on end of 2025. - Target Completion : end of 2025
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL * Customer is available for 3days (18~20 May) for source inspection. therfore source schedule & plan need to be adjusted. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> SKH commitment about AR purchasing is required for developing AR item #2 and #7 - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of March 2026 - SimOp installtion for neXT&LE will be completed on end of Jan 2026 * Plan : - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : TBD * Agenda : a. [M79] Over etch - some part EPD cluster don't close b. [M44] MeRiT_M44_Pattern copy fail of Fine mode ---> Ticket is closed c. [M26] [M44]_DC Mark Size & Scanning ---> Ticket is closed d. [M44] Abnormal EPD ---> Ticket is closed e. [M44] EUV PSM etching - Corner ---> Ticket is closed f. [M44] EUV PSM_Set up the Slope EPD in SKH ---> Ticket is closed
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59/ 61) - Action: Issue tracing in progress - Recovery attempt: Scheduled for Thursday
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA Matlab runtime error occurring for over 5 defect sites analysis (12/08) * Task : To give POA for current issue. * Action: Suggested to deleted cache folders (C:\FAVOR\AIMS AutoAnalysis\Matlab\McrCache) 1) (Resolved by re-installing AAA server s/w by customer on 15th Dec. * Result: Deleting cache folders does not work for this issue, deeper investigation required with HQ. 1) Result: OK. (15th Dec) - Temporary solution: reinstall AAA  can proceed 10+ defect site analysis
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AAA (ByungWan) | * Situation: AIMS 1x (2nd) S09 shown abnormal hole pattern (12/02) * Task: find out root cause * Action: Measured with CAA mask and shared to HQ. (Suspect Vibration) 1) H/W plan to visit and follow up POA2 provided HQ. and suspect NA Motor may have an issue on 16th Dec * Result: (HW: Action taken: CW51. Resolved)
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task : AIMS 1x CD delta matching * Action: HQ propose to measure new PDM mask and investigate it * Result: All type of defect were measured. Measure data was shared on 10.10 to HQ * Plan: HQ evaluation is on-going. [CW44]
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: HQ conduct simulation and share the report (December 17th) * Plan: Perform the process on the customer mask | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Situation: SK hynix have feature request in PROVE. * Task : Understand the feature reqeusts and expectations * Action: Scheduled the meeting for January 7th * Result: N/A * Plan: Customer Meeting > Review the requirements > Update to the HQ to further discuss to support it.
| PROVE | High Resolution (Dev) | * Workshop schedule: 24th Sep. * Pitch defining ZEISS and customer table will be shared by this week for internal (CW46) by HyeRim
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP Schedule by End of Jan 1) Target Completion : 9th Jan 2026 (Delay due to evalulation only AIMS. No AFM supported in customer) 2) ATP On going : 10th Nov ~ in Progress * MoSi PSM --> Remaining items : Broken line & Small extension Depo.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Mask Alignment failure - (40% of production volume) - AIMS Fab Neo F-ATP * Task : Need to adjust optic beam path. HQ support needed * Action: HQ H/W Engineer plan to dispatch in CW04 * Result: N/A * Plan: fATP sign off may proceed, once mask alingnment done with customer mask (CW05)
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD

## CW03
Reporting Part |  |  |  | None Reporting Part
2026-01-13 | CW03
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource | * KiWon, Cho : Business Trip to HQ (1/10 ~ 2/01) : 1. FAVOR 3.1 Pre-installation (Jena) - Samsung DFI Upgrade 관련 2. PROVE LRM & High Performance Mode - SEC & SK hynix 3. AIMS EUV WLCD at OKO - SK hynix
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Remaining items for Sign-off : Apps : - SW 5.6.0 upgrade : End of Jan 2026 - RS4 contamination test : 12nd Dec ~ TBD Service : - EFEM interlock installation : CW03 * Target for Sign-off : end of Jan 2026. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
| Repair | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Period : Option1: 5~18 April. / Option2: 10~23 May / Option3: 7~20 June. by Sasung. HQ feedback is required. - Items : 1. Delta column evaluation 2. PT based EUV PSM evaluation on LE tool --> HQ need to confirm suggsted items. 2. Delta Coulmn Performance Evaluation * 24th Dec. Samsung has provided feedback to ZEISS for evaluation items
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document.
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Priority 1. Improvement of selectivity up to 300% with new gas chemistry Priority 2. Ta vs. Cr buffer layer etch performance with new gas chemistry. * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement until end of Jan 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q1 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Waiting feedback from HQ.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | * Situation: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: suspecting rotated mask inside pod, requested further information to customer. * Plan: Pending for result files.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Customer shared the EUVR data (December 17th) * Plan: HQ prepare the report + Samsung measure AIMS EUV data for uniformity check (Schedule not fixed)
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data * Plan: HQ prepare the report
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 * Task : Job creation automation preparation * Action: Share first version of automation document to customer * Plan: Have updated file to customer on Jan 19th and have a call on Jan 20th
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS shared some idea to test for camera meter and interferometer on blank 1&2 * Plan: Samsung measure dense EUVR  ZEISS shared measurement coordinate for blank 1&2 as well as blank 6~7
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: HQ prepare slides that what will be implemented in next FTM version and share it to customer +Follow up on the items that discussed with Samsung for job automation (FTM modification scheduled to be released by 2026 April)
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (open in CW51 2025) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Check network status between Tool PC and FAVOR, some action items from HQ (restart FTM service, open port etc) *Plan: HQ think about if it is related to updated FTM version 4.0.0 itself
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung * Plan: Have customer feedback
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. * Plan: Fix the favor on scheduled date. (Plan: 2/06)
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: Evaluation of TTTM signature on PROVE neXT * Task: Customer will measure Same grid mask that is used for IPRO tool TTTM at PROVE next without TTTM calibration file. * Action: Compare the result with IPRO to check the signature of IPRO on PROVE tool. * Result: Still waiting for the measurement from the customer * Plan: Discuss further in next TTTM session with SAMSUNG
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Tool Dev. | * Customer Meeting : 9th Feb. Need to suggest - the week of SEMICON Korea
| PROVE | Pellicle Test | * Situation: Preparation for EUV pellicle demo on PROVE tools * Task: Customer plans to conduct a pellcile demo between 2Q and 3Q * Action: Collected Pellicle specification information from the customer, customer will evaluate loading / unloading and measurement feasibility * Result: Demo has not been conducted yet; evaluation results are pending * Plan: HQ will provide feedback on the proposed test plan, and next steps will be aligned with the customer accordingly.
| Repair | LE #1(M79) | 1. M79 ATP Pending items * Priority : Low * Situation : Remaining Pending items. * Task / Action plan. a. DUV Edge profile improvement - Customer will confirm on end of 2025. - Target Completion : end of 2025
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL * Customer is available for 3days (18~20 May) for source inspection. therfore source schedule & plan need to be adjusted. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo evaluation. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> Key function which need to be improvement until 2026 for AR purchasing in SKH. * neXT : Fine contour pattern copy, * LE : Defect centering error. - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of March 2026 - SimOp installtion for neXT&LE will be completed on end of Jan 2026 --> SKH has reqeusted to extend AR evaluation license to end of 2026. * Plan - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : TBD * Agenda : a. [M79] Over etch - some part EPD cluster don't close b. [M44] MeRiT_M44_Pattern copy fail of Fine mode ---> Ticket is closed c. [M26] [M44]_DC Mark Size & Scanning ---> Ticket is closed d. [M44] Abnormal EPD ---> Ticket is closed e. [M44] EUV PSM etching - Corner ---> Ticket is closed f. [M44] EUV PSM_Set up the Slope EPD in SKH ---> Ticket is closed
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59/ 61) - Action: Issue tracing in progress - Recovery attempt: Scheduled for Thursday
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA Matlab runtime error occurring for over 5 defect sites analysis (12/08) * Task : To give POA for current issue. * Action: Suggested to deleted cache folders (C:\FAVOR\AIMS AutoAnalysis\Matlab\McrCache) 1) (Resolved by re-installing AAA server s/w by customer on 15th Dec. * Result: Deleting cache folders does not work for this issue, deeper investigation required with HQ. 1) Result: OK. (15th Dec) - Temporary solution: reinstall AAA  can proceed 10+ defect site analysis
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AAA (ByungWan) | * Situation: AIMS 1x (2nd) S09 shown abnormal hole pattern (12/02) * Task: find out root cause * Action: Measured with CAA mask and shared to HQ. (Suspect Vibration) 1) H/W plan to visit and follow up POA2 provided HQ. and suspect NA Motor may have an issue on 16th Dec * Result: (HW: Action taken: CW51. Resolved)
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task : AIMS 1x CD delta matching * Action: HQ propose to measure new PDM mask and investigate it * Result: Done evaluation by HQ. HQ will provide Proposal of AIMS 1x specification * Plan: will have pre internal meeting on 1/20 and customer meeting during WK05
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: HQ conduct simulation and share the report (December 17th) * Plan: Perform the process on the customer mask | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Status: A customer has inquired to have desired feature in PROVE. * Task : Align a meeting to gather detailed requirements and understand the customer’s expectations * Action: Schedule Customer Workshop to describe PROVE’s SW features. * Result: The workshop will take place on Feb 12th at CJ office. (2/12) * Plan: Prepare workshop plan and materials.
| PROVE | High Resolution (Dev) | * Customer Meeting : 10th Feb. Confirmed - the week of SEMICON Korea
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP Schedule by 23rd Jan. 1) Target Completion : 23rd Jan 2026 (Delay due to evalulation only AIMS. No AFM supported in customer) 2) ATP On going : 10th Nov ~ in Progress * MoSi PSM --> Remaining items : Broken line & Small extension Depo.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Mask Alignment failure - (40% of production volume) - AIMS Fab Neo F-ATP * Task : Need to adjust optic beam path. HQ support needed * Action: HQ H/W Engineer plan to dispatch in CW04 * Result: N/A * Plan: fATP sign off may proceed, once mask alingnment done with customer mask (CW05)
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD

## CW04
Reporting Part |  |  |  | None Reporting Part
2026-01-13 | CW03
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource | * KiWon, Cho : Business Trip to HQ (1/10 ~ 2/01) : 1. FAVOR 3.1 Pre-installation (Jena) - Samsung DFI Upgrade 관련 2. PROVE LRM & High Performance Mode - SEC & SK hynix 3. AIMS EUV WLCD at OKO - SK hynix
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Remaining items for Sign-off : Apps : - SW 5.6.0 upgrade : End of Jan 2026 - RS4 contamination test : 12nd Dec ~ TBD Service : - Particle issue. * Target for Sign-off : CW05. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
| Repair | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Period : Option1: 5~18 April. / Option2: 10~23 May / Option3: 7~20 June. by Sasung. HQ feedback is required. - Items : 1. Delta column evaluation 2. PT based EUV PSM evaluation on LE tool --> HQ need to confirm suggsted items. 2. Delta Coulmn Performance Evaluation * 24th Dec. Samsung has provided feedback to ZEISS for evaluation items
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document.
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Priority 1. Improvement of selectivity up to 300% with new gas chemistry Priority 2. Ta vs. Cr buffer layer etch performance with new gas chemistry. * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement until end of Jan 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q1 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Waiting feedback from HQ.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | * Situation: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Full fields demos (2 demos) * Task : One Full fields demo on Feb with demo tool / The other full fields demo on Mar with alpha or beta tool * Action: * Plan: Share available demo schedule to customer
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Customer shared the EUVR data (December 17th) * Plan: HQ prepare the report + Samsung measure AIMS EUV data for uniformity check (Schedule not fixed)
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data * Plan: HQ prepare the report
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 * Task : Job creation automation preparation * Action: Share first version of automation document to customer * Plan: Have updated file to customer on Jan 19th and have a call on Jan 20th
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS shared some idea to test for camera meter and interferometer on blank 1&2 * Plan: Samsung measure dense EUVR  ZEISS shared measurement coordinate for blank 1&2 as well as blank 6~7
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: RegC : HQ prepare slides that what will be implemented in next FTM version and share it to customer(Jan 23rd) +Follow up on the items that discussed with Samsung for job automation (FTM modification scheduled to be released by 2026 April) CDC : To convince customer to use FTM --> HQ prepare the slides to explain .dat file check is not possible
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (open in CW51 2025) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Check network status between Tool PC and FAVOR, some action items from HQ (restart FTM service, open port etc) *Plan: HQ think about if it is related to updated FTM version 4.0.0 itself
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung * Plan: Have customer feedback (Jan 23rd)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. * Plan: Fix the favor on scheduled date. (Plan: 2/06)
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: Evaluation of TTTM signature on PROVE neXT * Task: Customer will measure Same grid mask that is used for IPRO tool TTTM at PROVE next without TTTM calibration file. * Action: Compare the result with IPRO to check the signature of IPRO on PROVE tool. * Result: Still waiting for the measurement from the customer * Plan: Discuss further in next TTTM session with SAMSUNG
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Tool Dev. | * Customer Meeting : 9th Feb. Need to suggest - the week of SEMICON Korea
| Repair | LE #1(M79) | 1. M79 ATP Pending items * Priority : Low * Situation : Remaining Pending items. * Task / Action plan. a. DUV Edge profile improvement - Customer will confirm on end of 2025. - Target Completion : end of 2025
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL * Customer is available for 3days (18~20 May) for source inspection. therfore source schedule & plan need to be adjusted. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo evaluation. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> Key function which need to be improvement until 2026 for AR purchasing in SKH. * neXT : Fine contour pattern copy, * LE : Defect centering error. - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of March 2026 - SimOp installtion for neXT&LE will be completed on end of Jan 2026 --> SKH has reqeusted to extend AR evaluation license to end of 2026. * Plan - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : TBD * Agenda : a. [M79] Over etch - some part EPD cluster don't close b. [M44] MeRiT_M44_Pattern copy fail of Fine mode ---> Ticket is closed c. [M26] [M44]_DC Mark Size & Scanning ---> Ticket is closed d. [M44] Abnormal EPD ---> Ticket is closed e. [M44] EUV PSM etching - Corner ---> Ticket is closed f. [M44] EUV PSM_Set up the Slope EPD in SKH ---> Ticket is closed
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59/ 61) - Action: Issue tracing in progress - Recovery attempt: Scheduled for Thursday
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: MA refine * Task: Since customer reported several spiral search on vis and uv, redefinition for MA was requested. * Action: MA calibration held on 15th of Jan. * Result: Was able to jump spiral search for customer mask's vis 1,2 uv 1,2, but was not able to improve uv3. CAA mask calibrated. Will continue MA on FF2 patch
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA Matlab runtime error occurring for over 5 defect sites analysis (12/08) * Task : To give POA for current issue. * Action: Suggested to deleted cache folders (C:\FAVOR\AIMS AutoAnalysis\Matlab\McrCache) 1) (Resolved by re-installing AAA server s/w by customer on 15th Dec. * Result: Deleting cache folders does not work for this issue, deeper investigation required with HQ. 1) Result: OK. (15th Dec) - Temporary solution: reinstall AAA  can proceed 10+ defect site analysis
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AAA (ByungWan) | * Situation: AIMS 1x (2nd) S09 shown abnormal hole pattern (12/02) * Task: find out root cause * Action: Measured with CAA mask and shared to HQ. (Suspect Vibration) 1) H/W plan to visit and follow up POA2 provided HQ. and suspect NA Motor may have an issue on 16th Dec * Result: (HW: Action taken: CW51. Resolved)
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task : AIMS 1x CD delta matching * Action: HQ propose to measure new PDM mask and investigate it * Result: Done evaluation by HQ. HQ will provide Proposal of AIMS 1x specification * Plan: will have pre internal meeting on 1/20 and customer meeting during WK05
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Plan: Deliver the mask to customer on Jan 20th | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Status: A customer has inquired to have desired feature in PROVE. * Task : Align a meeting to gather detailed requirements and understand the customer’s expectations * Action: Schedule Customer Workshop to describe PROVE’s SW features. * Result: The workshop will take place on Feb 10th at CJ office. (2/10) -> Need to be changed * Plan: Prepare workshop plan and materials.
| PROVE | High Resolution (Dev) | * Customer Meeting : 10th Feb. Confirmed - the week of SEMICON Korea
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP Schedule by 23rd Jan. 1) Target Completion : 23rd Jan 2026 (Delay due to evalulation only AIMS. No AFM supported in customer) 2) ATP On going : 10th Nov ~ in Progress * MoSi PSM --> Remaining items : Broken line & Small extension Depo.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Mask Alignment failure - (40% of production volume) - AIMS Fab Neo F-ATP * Task : Need to adjust optic beam path. HQ support needed * Action: HQ H/W Engineer plan to dispatch in CW04 * Result: N/A * Plan: fATP sign off may proceed, once mask alingnment done with customer mask (CW05)
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: N/A
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Korean language patch for fab neo * Task : To provide korean language patch for the tool * Action: searching for right patch package, will proceed this week. * Result: N/A
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD

## CW05
Reporting Part |  |  |  | None Reporting Part
2026-01-27 | CW05
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource | * KiWon, Cho : Business Trip to HQ (1/10 ~ 2/01) : 1. FAVOR 3.1 Pre-installation (Jena) - Samsung DFI Upgrade 관련 2. PROVE LRM & High Performance Mode - SEC & SK hynix 3. AIMS EUV WLCD at OKO - SK hynix * TaeHoon, Kim : DNP Japan support (1/22~2/7)
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Pending items. - SW 5.6.0 upgrade. - RS4 contamination test. - Reduce backside particle. * Target for Sign-off : b/o Feb due to align pending items (Backside particle spec) | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. (Hold) | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
| Repair | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Period : HQ prefer 7~20 June. - Items : 1. Delta column evaluation 2. PT based EUV PSM evaluation on LE tool --> HQ need to confirm suggsted items. 2. Delta Coulmn Performance Evaluation * 24th Dec. Samsung has provided feedback to ZEISS for evaluation items
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document. Auto Repair discussion for open items will be started with 4.15 SW version release.(b/o Feb)
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Priority 1. Improvement of selectivity up to 300% with new gas chemistry Priority 2. Ta vs. Cr buffer layer etch performance with new gas chemistry. * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement until end of Jan 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q2 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Waiting feedback from HQ.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | * Situation: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| AAA (P4) | AAA FAVOR(P4) | * Situation: P4 FAVOR 3.0 AAA down * Task : AAA service stop status after AAA program closed. AAA service start failed. * Action: Investigated Window Log, Server Reboot * Result: For Window log, Lack C drive storage caused the issue. After reboot, AAA is working. Delete the file under the path ( C  FAVOR  Aims Auto Analysis  Matlab  Logging * Plan : Secure C drive storage and monitoring. (Need to consider chaning of storage drive)
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Full fields demos (2 demos) * Task : One Full fields demo on Feb with demo tool / The other full fields demo on Mar with alpha or beta tool * Action: Share available demo schedule on Feb with demo tool  m/o Feb after checking PW with current demo tool status • Plan: Check PW as well as available demo schedule for Mar
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Figured out there was human error during RegC process * Plan: Redo the process
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data * Plan: HQ prepare the report (Scheduled by b/o Feb)
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 * Task : Job creation automation preparation * Action: Share first version of automation document to customer * Plan: Have updated file to customer on Jan 19th and have a call on Jan 20th
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it * Plan: Wait for HVM tool (alpha or beta)
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: - RegC : RegC : Aligned between ZEISS and Samsung for the new feature required for automation  New FTM need to be released - CDC : To convince customer to use FTM --> HQ prepare the slides to explain .dat file check is not possibl e
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (open in CW51 2025) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Check network status between Tool PC and FAVOR, some action items from HQ (restart FTM service, open port etc) *Plan: Perform action item (to check if port is open properly) by HQ (Tool time requested to Jan 28th)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung * Plan: Have customer feedback (Jan 23rd)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| Tuning | ForTune EUV (Ji HyeRim) (DongHoon Koo) | * Situation: Overcorrection from F601 process (Resolved issue) * Task : Figure out the reason of overcorrection (At the moment customer think mask bow from z height offset is the rootcause) * Action: HQ service engineer and SSC HW engineers figured out that there was offset  Offset calibration is done * Plan: Share the report to customer including feedback for customer questions
| PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. * Plan: Fix the favor on scheduled date. (Plan: 2/06)
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: Evaluation of TTTM signature on PROVE neXT * Task: Customer will measure Same grid mask that is used for IPRO tool TTTM at PROVE next without TTTM calibration file. * Action: Compare the result with IPRO to check the signature of IPRO on PROVE tool. * Result: Still waiting for the measurement from the customer * Plan: Discuss further in next TTTM session with SAMSUNG
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Tool Dev. | * Customer Meeting : 9th Feb. Confirmed at K1 gate
| Repair | LE #1(M79) | 1. M79 ATP Pending items * Priority : Low * Situation : Remaining Pending items. * Task / Action plan. a. DUV Edge profile improvement - Customer will confirm on end of 2025. - Target Completion : end of 2025
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL * Customer is available for 3days (18~20 May) for source inspection. therfore source schedule & plan need to be adjusted. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo evaluation. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> Key function which need to be improvement until 2026 for AR purchasing in SKH. * neXT : Fine contour pattern copy, * LE : Defect centering error. - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of March 2026 - SimOp installtion for neXT&LE will be completed on end of Jan 2026 --> SKH has reqeusted to extend AR evaluation license to end of 2026. * Plan - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : e/o Feb. * Agenda : - Agenda will be fixed with SKH.
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59/ 61) - Action: Issue tracing in progress - Recovery attempt: Scheduled for Thursday
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: MA refine * Task: Since customer reported several spiral search on vis and uv, redefinition for MA was requested. * Action: MA calibration held on 15th of Jan. * Result: Was able to jump spiral search for customer mask's vis 1,2 uv 1,2, but was not able to improve uv3. CAA mask calibrated. Will continue MA on FF2 patch
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task : AIMS 1x CD delta matching * Action: HQ propose to measure new PDM mask and investigate it * Result: Done evaluation by HQ. HQ will provide Proposal of AIMS 1x specification * Plan: HQ will propose new guideline based on analysis result on Customer Call on 1/27
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Plan: Have measurement result (registration & overlay) from customer - Expecting to have wafer result in the m/o Feb | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Status: A customer has inquired to have desired feature in PROVE. * Task : Align a meeting to gather detailed requirements and understand the customer’s expectations * Action: Schedule Customer Workshop to describe PROVE’s SW features. * Result: The workshop will take place on Feb 10th at CJ office. (2/10) -> Need to be changed * Plan: Prepare workshop plan and materials.
| PROVE | High Resolution (Dev) | * Customer Meeting : 10th Feb. Confirmed - the week of SEMICON Korea
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP completion : 22nd Jan. * ATP sign-off : Pending items discussion on going (Target: in Feb.) - Customer will review for pending items. - AMX and AM match between MG45 and MG neo
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Mask Alignment failure - (40% of production volume) - AIMS Fab Neo F-ATP * Task : Need to adjust optic beam path. HQ support needed * Action: HQ H/W Engineer plan to dispatch in CW04: Completed in CW04 * Result: fATP - customer sign off : Completed in 26th Jan
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: N/A
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Korean language patch for fab neo * Task : To provide korean language patch for the tool * Action: searching for right patch package, will proceed this week. * Result: N/A
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD
PKL | AIMS DUV | AIMS 1x | * Pick up : 2027.01.29 (at ZEISS factory)

## CW06
Reporting Part |  |  |  | None Reporting Part
2026-01-27 | CW05
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource | * TaeHoon, Kim : DNP Japan support (1/22~2/7)
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. F-ATP completion for Application process tuning : 5th Dec * Pending items. - SW 5.6.0 upgrade. - RS4 contamination test. - Reduce backside particle. * Target for Sign-off : Depends on the 5.6.0 SW release date --> Nadine will update on 4th Feb. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. (Hold) | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
| Repair | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Period : June 2026.(details need to be aligned) - Items : 1. Delta column evaluation 2. PT based EUV PSM evaluation on LE tool 2. Delta Coulmn Performance Evaluation * ZEISS will provide feedback for Demo items in Feb.
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document. Auto Repair discussion for open items will be started with 4.15 SW version release.(b/o Feb)
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Priority 1. Improvement of selectivity up to 300% with new gas chemistry Priority 2. Ta vs. Cr buffer layer etch performance with new gas chemistry. * Plan : ZEISS will provide Samsung the 1st report for selectivity improvement until end of Jan 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q2 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Waiting feedback from HQ. 4. HQ on site customer meeting * Plan : CW12 * HQ participant : Felix * Agenda : Pt based EUV PSM evalution update.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | * Situation: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | • Situation: Save classification code when using rff. (1/25) • Task : Customer request that classification code has to be seen in result files when using rff files. • Action: NA • Result: NA • Plan: Need to narrow down which tool/customer first.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | • Situation: AIMSHOST-Error _ unhandled exception • Task: SECS GEM bug investigation required. • Action: Open sustaining ticket for this issue. • Result: NA • Plan: Log export handled by HW team.
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| AAA (P4) | AAA FAVOR(P4) | * Situation: P4 FAVOR 3.0 AAA down * Task : AAA service stop status after AAA program closed. AAA service start failed. * Action: Investigated Window Log, Server Reboot * Result: For Window log, Lack C drive storage caused the issue. After reboot, AAA is working. Delete the file under the path ( C  FAVOR  Aims Auto Analysis  Matlab  Logging ) * Plan: Secure C drive storage and will modify ServerConfiguration.xml to stop Matlab logging
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Full fields demos (2 demos) * Task : One Full fields demo on Feb with demo tool / The other full fields demo on Mar with alpha or beta tool * Action: Share available demo schedule on Feb with demo tool  m/o Feb after checking PW with current demo tool status • Plan: Check PW as well as available demo schedule for Mar
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Figured out there was human error during RegC process * Plan: Redo the process
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data * Plan: HQ prepare the report (Scheduled by b/o Feb)
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 Application part * Task : Job creation automation preparation * Action: Send Gantt chart regarding automation / HW / Application items to HQ (Jan 20th) * Plan: Waiting for HQ feedback for the Gantt chart * Support needed : Schedule for FTM ready is required ASAP to discuss job automation
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it * Plan: Wait for HVM tool (alpha or beta)
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: RegC : Aligned between ZEISS and Samsung for the new feature required for automation  New FTM need to be released CDC : Customer request was shared to HQ but rule is not clear for HQ  To share clear rule that samsung required
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file * Plan: Wait for HQ feedback
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung * Plan: Have customer feedback (Jan 23rd)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| Tuning | ForTune EUV (Ji HyeRim) (DongHoon Koo) | * Situation: Overcorrection from F601 process (Resolved issue) * Task : Figure out the reason of overcorrection (At the moment customer think mask bow from z height offset is the rootcause) * Action: HQ service engineer and SSC HW engineers figured out that there was offset  Offset calibration is done * Plan: Share the report to customer including feedback for customer questions
| PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. * Plan: Fix the favor on scheduled date. (Plan: 2/06)
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. * Plan: Monitor the progress of the master tool transition.
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Tool Dev. | * Customer Meeting : 9th Feb. Confirmed at K1 gate
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 22nd May 2026 * Attendance from SKH : 박인영 TL * Customer is available for 3days (18~20 May) for source inspection. therfore source schedule & plan need to be adjusted. 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo evaluation. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> Key function which need to be improvement until 2026 for AR purchasing in SKH. * neXT : Fine contour pattern copy (2Q 2026), * LE : Defect centering error (4Q 2026). - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of June 2026 - SimOp installtion for neXT&LE will be completed on end of Feb 2026 * Plan - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation. 2. HQ on site customer meeting * Plan : CW12 * HQ participant : Felix * Agenda : EUV PSM undercut update.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : e/o Feb. * Agenda : - Agenda will be fixed with SKH.
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attache VM with new. : OK (valide for root cause. Possible corruction of network) - Recovery attempt: Scheduled for Thursday
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: FF2 upgrade (CW04) * Task : FF2 upgrade (FAVOR upgrade for apps), Smoke tests * Action: FAVOR FF2 upgrade and verification planned on Wednesday/Thursday. * Result: FF2 upgrade completed, smoke test passed.
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task: Defect Size measured differently between AIMS 1x #4 & #6 * Action: HQ investigates both AIMS 1x Images * Result: SK hynix -ZEISS cannot meet the SK Hynix Spec. SK hynix cannot accpet Spec in data because Average value did not reflect Fluctuated data. * Plan: HQ & SK Hynix will have further discussion on 2/4.
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Plan: Have measurement result (registration & overlay) from customer - Expecting to have wafer result in the m/o Feb | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Status: A customer has inquired to have desired feature in PROVE. * Task : Align a meeting to gather detailed requirements and understand the customer’s expectations * Action: Schedule Customer Workshop to describe PROVE’s SW features. * Result: The workshop will take place on Feb 24th at CJ office. * Plan: Prepare workshop plan and materials.
| PROVE | High Resolution (Dev) | * Customer Meeting : 10th Feb. Confirmed - the week of SEMICON Korea
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP completion : 22nd Jan. * ATP sign-off : Pending items discussion is on going (Target: in Feb.) - Pending items : AMX and AM modificaiton support.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: ongoing (Visiting schedule in CW06)
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | • Situation: Windows Korean patch • Task : to patch windows language pack in fab neo • Action: given .cab data was not successfully installed. • Result: requires turn-around solution
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD
PKL | AIMS DUV | AIMS 1x | * Pick up : 2027.01.29 (at ZEISS factory)

## CW07
Reporting Part |  |  |  | None Reporting Part
2026-01-27 | CW05
Customer | FoB | Green: Updated White: No Up. | * Highlight / Updated
HQ | All | Resource
| Repair | LE#1 (m 85) | 1. Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) * Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: 23rd Oct, 2025 * Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
| Repair | LE#1 (m 85) | 3. EUV etch ESB signal issue (Priority: Low) * Situation: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. * Result : ESB signal monitoring is completed. * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#2 (m 93) | 1. F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) * Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. * Completion of SiN: Nov 24th 2025 * Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
| Repair | LE#2 (m 93) | 2) EUV etch ESB signal issue : Same as LE#1 * Plan: Samsung will decide for using current video signal setting.(Target Completion : Jan 2026)
| Repair | LE#3 (m106) in P4 | 1. Sign-off completed : 5th Feb 2026. * Pending items. - SW 5.6.0 upgrade. - RS4 contamination test. - Reduce backside particle. | * Completed ZAN1: 16th Oct. 2025
| Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. 1) SECS/GEM Open Items - Target Completion : Jan 2026
| Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Situation a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task / Action plan a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD
| Repair | Samsung Monthly Meeting. (Hold) | * Updated on 8th Dec : 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b . MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are underdiscussion with Samsung. 4. AutoRepair 4.0 에 대한 개발/투자/Auto Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
| Repair | MeRiT AE | 1. MeRiT AE evaluation * Samsung live demo in Rosdorf - Period : June 2026.(details need to be aligned) - Items : 1. Delta column evaluation 2. PT based EUV PSM evaluation on LE tool 2. Delta Coulmn Performance Evaluation - ZEISS has provided feedback to Samsung about Demo items (9th Feb) - bi-monthly customer meeting will be aligned.
| Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off : Waiting feedbac from Samsung about start AR ATP with specification document. Auto Repair discussion for open items will be started with 4.15 SW version release.(b/o Feb)
| Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Situation : Samsung has pland to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Priority 1. Improvement of selectivity up to 300% with new gas chemistry Priority 2. Ta vs. Cr buffer layer etch performance with new gas chemistry. * Plan : ZEISS will provide Samsung the status update on March and TRM (April) 2. New Gas chemisty for EUV PSM High-NA * New Gas candidate need to be infromed to Samsung to prepare Samsung EHS. 3. Live demo on Q1 2026 * Situation : Samsung has requested a evaluation of Pt based EUV PSM during Q2 2026 with Delta column live demo * Task : fesibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : ZEISS has provided feedback to Samsung about Demo items (9th Feb) 4. HQ on site customer meeting * Plan : CW12 * HQ participant : Felix * Agenda : Pt based EUV PSM evalution update.
| Repair | MAA | 1. MAA evaluation (MeRiT Auto Analysis) * Situation : Samsung is interested in AIS (Aerial Image Simulation) feature on MAA * Task : Feature define MAA and AIS for Samsung. * Action : Samsung has suggsted JDP with specific conditions. * Plan : ZEISS will provide feedback to Samsung about JDP proposal.
| Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Situation: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Situation: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
| AIMS EUV 1.0 | AIMS EUV 1.0 (C2) (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Situation: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
| AAA EUV (AAA EUV) | AAA EUV (P4) (Cho, KiWon) | * Situation: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Situation: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Situation: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | * Situation: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close.
| AIMS EUV (Advanced R&D) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | • Situation: Save classification code when using rff. (1/25) • Task : Customer request that classification code has to be seen in result files when using rff files. • Action: NA • Result: NA • Plan: Need to narrow down which tool/customer first.
| AIMS EUV 3.0 | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | • Situation: AIMSHOST-Error _ unhandled exception • Task: SECS GEM bug investigation required. • Action: Open sustaining ticket for this issue. • Result: NA • Plan: Log export handled by HW team.
| AIMS DUV | AIMS 1x (SR1) (WonTae Kim) | [TTTM] S *1 AIMS-1x [One of discussion items with Samsung on 5th Nov] * Situation: S *1 - AIMS 1x Intensity Diffe *ence * Task : AIMS 1x TTTM. Need to Imp *ove diff *action image * Action: H/W team p *ovided co * *ection activity in CW46 * *esult: Good befo *e MAA cal. Not Good: Afte * MAA cal * Plan: H/W team is checking with HQ whethe * MAA need to be *eplaced
| AIMS DUV | AIMS 1x (NRD) (Byungwan) | [TTTM] NRD AIMS-1x * Situation: AIMS 1x NRD SW roll back to 6.12 from 6.15 * Task: Plan to be upgraded once 6.18.2 released (mid of Dec 2025) * Action: follow up s/w upgrade * Result: N/A * Plan: need to check in the m/o Dec for the release of 6.18.2 | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
| AAA | AAA (FAVOR) (Kim, WonTae) | * Situation: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
| AAA | AAA with automation | * Situation: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
| AAA (P4) | AAA FAVOR(P4) | * Situation: P4 FAVOR 3.0 AAA down * Task : AAA service stop status after AAA program closed. AAA service start failed. * Action: Investigated Window Log, Server Reboot * Result: For Window log, Lack C drive storage caused the issue. After reboot, AAA is working. Delete the file under the path ( C  FAVOR  Aims Auto Analysis  Matlab  Logging ) * Plan: Secure C drive storage and will modify ServerConfiguration.xml to stop Matlab logging
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Full fields demos (2 demos) * Task : One Full fields demo on Feb with demo tool / The other full fields demo on Mar with alpha or beta tool * Action: Share available demo schedule on Feb with demo tool  m/o Feb after checking PW with current demo tool status • Plan: Check PW as well as available demo schedule for Mar
| Tuning CDC EUV | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Situation: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Figured out there was human error during RegC process * Plan: Redo the process
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data * Plan: HQ prepare the report (Scheduled by b/o Feb)
| Tuning CDC EUV | ForTune MLM (Kim, WonTae) | * Situation: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: SECS GEM 300 Application part * Task : Job creation automation preparation * Action: Send Gantt chart regarding automation / HW / Application items to HQ (Jan 20th) * Plan: Waiting for HQ feedback for the Gantt chart * Support needed : Schedule for FTM ready is required ASAP to discuss job automation
| Tuning CDC EUV | ForTune MLM (HyeRim) | * Situation: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it * Plan: Wait for HVM tool (alpha or beta)
| Tuning | ForTune DUV (HyeRim) | * Situation: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: RegC : Aligned between ZEISS and Samsung for the new feature required for automation  New FTM need to be released CDC : Customer request was shared to HQ but rule is not clear for HQ  To share clear rule that samsung required
| Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Situation: Fortune DUV SW upgrade 5.9.3 – FTM connection failure * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file * Plan: Wait for HQ feedback
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung * Plan: Have customer feedback (Jan 23rd)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Pixel non uniformity * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: Mask thickness deviation between E601(SR1)&E605(P4) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May and shared it to ZEISS last week * Plan: ZEISS look into the result
| Tuning | ForTune EUV (Ji HyeRim) | * Situation: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
| Tuning | ForTune EUV (Ji HyeRim) (DongHoon Koo) | * Situation: Overcorrection from F601 process (Resolved issue) * Task : Figure out the reason of overcorrection (At the moment customer think mask bow from z height offset is the rootcause) * Action: HQ service engineer and SSC HW engineers figured out that there was offset  Offset calibration is done * Plan: Share the report to customer including feedback for customer questions
| PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | * Situation: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. * Plan: Fix the favor on scheduled date. (Plan: 2/06)
| PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
| PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
| PROVE | neXT (DongHoon, Koo) | [TTTM] * Situation: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. * Plan: Monitor the progress of the master tool transition.
| PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Situation: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
| PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
| PROVE Hi-Res | Tool Dev. | * Customer Meeting : 9th Feb. Confirmed at K1 gate
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 20nd May 2026 * Attendance from SKH : 박인영 TL 2. NOCl only recipe request * Priority : Middle * Situation : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
| Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Situation : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo evaluation. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> Key function which need to be improvement until 2026 for AR purchasing in SKH. * neXT : Fine contour pattern copy (2Q 2026), * LE : Defect centering error : improved by parameter adjustment. - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of June 2026 - SimOp installtion for neXT&LE will be completed on end of Feb 2026 * Plan - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
| Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Situation : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
| Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Situation : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : ZEISS will provide update SKH after evaluation. 2. HQ on site customer meeting * Plan : CW12 * HQ participant : Felix * Agenda : EUV PSM undercut update.
| Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : e/o Feb. * Agenda : - Agenda will be fixed with SKH.
| AIMS EUV | AIMS EUV 3.1 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Situation: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Situation: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Situation: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Situation: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
| AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attache VM with new. : OK (valide for root cause. Possible corruction of network) - Recovery attempt: Scheduled for Thursday
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: FF2 upgrade (CW04) * Task : FF2 upgrade (FAVOR upgrade for apps), Smoke tests * Action: FAVOR FF2 upgrade and verification planned on Wednesday/Thursday. * Result: FF2 upgrade completed, smoke test passed.
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search
| AIMS EUV | AIMS EUV 3.1 (Soonyoung Lee) | * Situation: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation
| AIMS DUV | AAA (SoonYoung) | * Situation: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
| AIMS DUV | AAA (SoonYoung) | * Situation: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
| AIMS DUV | AIMS 1x (WonTae) | * Situation: AIMS 1x TTTM * Task: Defect Size measured differently between AIMS 1x #4 & #6 * Action: HQ investigates both AIMS 1x Images * Result: SK hynix -ZEISS cannot meet the SK Hynix Spec. SK hynix cannot accpet Spec in data because Average value did not reflect Fluctuated data. * Plan: HQ & SK Hynix will have further discussion on 2/4.
| AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Situation: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
| AAA | AAA | * Situation: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
| AAA EUV | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
| ForTune | ForTune EUV (HyeRim) | * Situation: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Plan: Have measurement result (registration & overlay) from customer - Expecting to have wafer result in the m/o Feb | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
| PROVE (Demo) | PROVE neXT (DongHoon Koo) (HyeRim) | * Situation: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: 1) Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
| PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Status: A customer has inquired to have desired feature in PROVE. * Task : Align a meeting to gather detailed requirements and understand the customer’s expectations * Action: Schedule Customer Workshop to describe PROVE’s SW features. * Result: The workshop will take place on Feb 24th at CJ office. * Plan: Prepare workshop plan and materials.
| PROVE | High Resolution (Dev) | * Customer Meeting : 10th Feb. Confirmed - the week of SEMICON Korea
Tekscend | MeRiT | MG neo ( M141) (TaekKyoung) | 1. F-ATP completion : 22nd Jan. * ATP sign-off : Pending items discussion is on going (Target: in Feb.) - Pending items : AMX and AM modificaiton support. --> There is mentioned about recipe supprot in quotation.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Situation: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: ongoing (Visiting schedule in CW06)
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | • Situation: Windows Korean patch • Task : to patch windows language pack in fab neo • Action: given .cab data was not successfully installed. • Result: requires turn-around solution
PKL | Repair | MeRiT neXT | * The tool will be delivered in e/o Feb. 2027. 1. Source Inspection : TBD 2. ATP schedule : TBD
PKL | AIMS DUV | AIMS 1x | * Pick up : 2027.01.29 (at ZEISS factory)

## CW09
Cus. | FoB | Tool | Status / Task / Action / Result / Plan (Updated in Blue)
HQ | All | HQ visit | * 03/03 ~ 03/06 - AAA (Thomas Zuener) : SK hynix 3/3~3/4, Samsung 3/5 ~ 3/6 * 03/09 ~ 03/12 - Tuning in Samsung (Sami & Alex) : 3/9: SSC training ¦ 3/10~3/11: Samsung Meeting with ForTune DUV & ForTune MLM * 03/18 ~ 03/20 - MeRiT EUV PSM discussion (Felix) : 3/19 : SSC on-site meeting ¦ 3/20 : SK Hynix on-site meeting.
SEC | Repair | LE#1 (m 85) | * Final ATP Sign-off: Signed on 29th July 2025. (Pending Item: SiN Etch to be completd by Sep 2025) - Warranty start: Oct 2025, if ZEISS couldn't find a solution for SiN by then Samsung and ZEISS will discuss again for warranty extension. - Completion of SiN: 23rd Oct, 2025 - Compensation item: SSC suggsted Gas sensor parts as compensation item. waiting feedback from Samsung.
SEC | Repair | LE#1 (m 85) | * EUV etch ESB signal issue (Priority: Low) - Status: Min ESB signal fluctuation happens. but no impact in the tool operation. - Task: keeping stable ESB signal. - Action : Changed back to Samsung Video signal due to high Gap. - Result : ESB signal monitoring is completed. - Plan: Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#2 (m 93) | * F-ATP Schedule: Signed off on 29th July. (Pending Item: SiN Etch by Sep) - Warranty will start Oct 2025 : if ZEISS couldn't find a solution by then Samsung and ZEISS will discuss again for warranty extension. - Completion of SiN: Nov 24th 2025 - Compensation item: SSC has suggsted Samsung Gas sensor parts as compensatins. waiting feedback from Samsung.
SEC | Repair | LE#2 (m 93) | * EUV etch ESB signal issue : Same as LE#1 - Plan: Samsung will decide for using current video signal setting.(Target Completion : March 2026)
SEC | Repair | LE#3 (m106) in P4 | * Sign-off completed : 5th Feb 2026. [Pending items] - SW 5.6.0 upgrade, S/W released on 23rd Feb. - RS4 contamination test. - Reduce backside particle (H/W) | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | 1. F-ATP Schedule: Signed off on 29th July (Pending Item: SECS/GEM open items by Jan, 2026) - If SECS/GEM open items not solved on Jan 2026, Samsung will not do sing-off for LE#3(M106) 2. Pending items. [SECS/GEM Open Items] - 5.6.1 SW released on 23rd Feb. - Target Completion : March 2026
SEC | Repair | M50 neXT | 1. Ch8 liquid water upgrade for SiN etch process. (Priority : Low) - Status a. Samsung request an Upgrade of Ch8 from iced to liquid water. b. Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) c. ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. d. SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. - Task a. Required parts for upgrade need to be confirmed by HQ - Service Team need to communicate with HQ. - Target Completion : TBD - Action plan a. Priority of liquid water upgrade is low for Samsung. b. SSC asked decision to Samsung, go or stop for liquid water upgrade.
SEC | Repair | Samsung Monthly Meeting. (Hold) | [Updated on 8th Dec] 1. TRM 이후 Hi-NA 관련 후속조치. - ZEISS will provide update about fesibility test of Pt base EUV PSM with new gas chemistry. 2. LE 보상안 관련 진행사항 업데이트 a. EUV PSM module : Completed, but Recipe need to be replaced before end of May 2026 due to expired date. b. MeRiT office PC for LE#2 & LE#3 - Under discussion with HQ and Samsung d. Sentinel & FDC interface : - Under discussion 3. HighT 관련 전체 진행사항 - Completed on 24th Nov(LE#2), Compensation items are under discussion with Samsung. 4. Auto-Repair 4.0 에 대한 개발 / 투자 / Auto-Repair 3.0 pending 방향정리 - SSC has suggsted Samsung to start ATP discussion with documentation.
SEC | Repair | MeRiT AE | 1. MeRiT AE Demo [Samsung live demo in Rosdorf] - Period: June 2026.(details need to be aligned) - Items: a. Delta Coulmn Performance Evaluation b. PT based EUV PSM evaluation on LE tool 2. Delta Coulmn Performance Evaluation (Demo) - Demo items are roughly aligned, but it need to be discussed with Samsung for final decision. - Alignment meeting has been aligned on 11st March. 3. PT based EUV PSM evaluation on LE tool (Demo) - Alignment meeting has been aligned on 19th March (Felix will visit Samsung)
SEC | Repair | Auto Repair (with next) | 1. Auto Repair: Success rate: 40 % As of Nov 2025. But, no concern (production). Due to none SOW defect. 2. ATP Sign-Off: Waiting feedback from Samsung about start AR ATP with specification document. Auto Repair discussion for open items will be started with 4.15 SW version release.(b/o Feb)
SEC | Repair | EUV PSM Collaboration | 1. EUV PSM High-NA (Pt based) * Status : Samsung has plan to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : Priority 1. Improvement of selectivity up to 300% with new gas chemistry Priority 2. Ta vs. Cr buffer layer etch performance with new gas chemistry. * Plan : EUV PMS update meeting has been aligned on 19th March (Felix will visit Samsung) 2. New Gas chemistry for EUV PSM High-NA * New Gas candidate need to be informed to Samsung to prepare Samsung EHS. 3. Live demo on June 2026 * Status : Samsung has requested a evaluation of Pt based EUV PSM with Delta column live demo * Task : feasibility for Demo need to be confirmed by HQ. * Action : Samsung has provided HQ about test items. * Plan : Demo items alignment meeting has been aligned on 19th March (Felix will visit Samsung) 4. EUV PSM Mesh imprint issue on neXT and LE. * Status : Mesh imprint is visible after EUV PSM etch process. * Task : Samsung and ZEISS collaboration work to find root case. * Action : ZEISS will start discussion to find root case. * Plan : Samsung will provide ZEISS relevant data for Mesh imprint issue.
SEC | Repair | Tool Monitoring (with LE) | 1. Sentinel and Data center installation are completed for LE1 ~4 * ZEISS will provide update SW as following Roadmap until end of 2026
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | [Mask Alignment Failure] * Status: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
SEC | AAA | AAA EUV (P4) (Cho, KiWon) | * Status: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | - Status: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | * Status: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close.
SEC | AIMS EUV (Advanced) | AIMS EUV | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | • Status: Save classification code when using rff. (1/25) • Task : Customer request that classification code has to be seen in result files when using rff files. • Action: NA • Result: NA • Plan: Need to narrow down which tool/customer first.
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | • Status: AIMSHOST-Error _ unhandled exception • Task: SECS GEM bug investigation required. • Action: Open sustaining ticket for this issue. • Result: NA. • Plan: Log export handled by HW team.
SEC | AIMS DUV | AIMS 1x (SR1) | [TTTM] • Status: AIMS 1x in SR1 have an Intensity Difference. • Task : AIMS 1x TTTM. Need to Improve diff. image. • Action: H/W team provided correction activity in CW46. • Result: Good before MAA cal. Not Good: After MAA cal. • Plan: H/W team is checking with HQ whether MAA need to be replaced.
SEC | AIMS DUV | AIMS 1x (NRD) | [TTTM] • Status: AIMS 1x 6.18.2 SW need to be upgrade. • Task: SW upgrade • Action: NA • Result: No upgrade items found in ftp. • Plan: Target SW ver is changed to 6.18.3. waiting for releasing target version | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | * Status: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | * Status: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
SEC | AAA | AAA with automation | * Status: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
SEC | AAA | AAA FAVOR(P4) (WonTae) (KiWon) | * Status: P4 AAA, defect numbering in RNR jobs * Task : Difficulty to figure out Defect # and position identification * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, * Plan : Request HQ to review the P4 AAA RNR defect numbering logic and provide a fix
SEC | AAA | AAA FAVOR(P4) (WonTae) | * Status: P4 FAVOR 3.0 Multiple Process Error * Task : Matlab Error with process failure when multiple process is running * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. Escalated it to HQ * Plan : The log including abnormal event to HQ. will investigate it.
SEC | Tuning | ForTune MLM (HyeRim) | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Send some question about FTM and job automation to HQ (Feb 4th) • Plan: Waiting for HQ feedback for the Gantt chart & answers for the questions + discuss it during HQ on site visit on week 11
SEC | Tuning | ForTune MLM (HyeRim) | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (week of 15th Feb) • Action: PW has been obtained with blank 2 • Plan: It is delayed due to mask export issue. Once we fixe it, restart the process
| Tuning | ForTune MLM (HyeRim) | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | 1. Task: PIP Blank 8 (CDC EUV after RegC) : Israel * Status: Blank 8 mask process (2nd RegC after EUV CDC) * Task : HQ perform 2nd RegC after EUV CDC at HQ side * Action: Figured out there was human error during RegC process * Plan: Redo the process
SEC | Tuning | ForTune MLM (HyeRim) | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: Perform the process (done) + The mask is coming back to Korea • Plan: Once the mask is arrived in Korea, customer measure the results
SEC | Tuning | ForTune MLM (HyeRim) | • Situation: HVM tool introduction slides • Task : To share HVM tool introduction slides • Action: Ask to HQ to share the prepare the slides • Plan: ZEISS shared the slides to Samsung Feb 12th
SEC | Tuning | ForTune MLM (HyeRim) | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : b/o March)
SEC | Tuning | ForTune MLM (HyeRim) | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data * Plan: HQ prepare the report (Scheduled by b/o Feb)
SEC | Tuning | ForTune MLM (Kim, WonTae) | * Status: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
SEC | Tuning | ForTune MLM (HyeRim) | * Status: SECS GEM 300 Application part * Task : Job creation automation preparation * Action: Send Gantt chart regarding automation / HW / Application items to HQ (Jan 20th) * Plan: Waiting for HQ feedback for the Gantt chart * Support needed : Schedule for FTM ready is required ASAP to discuss job automation
SEC | Tuning | ForTune MLM (HyeRim) | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it * Plan: Wait for HVM tool (alpha or beta)
SEC | Tuning | ForTune DUV (HyeRim) | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) * Plan: RegC : Aligned between ZEISS and Samsung for the new feature required for automation  New FTM need to be released CDC : Customer request was shared to HQ but rule is not clear for HQ  To share clear rule that samsung required
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file * Plan: Wait for HQ feedback
SEC | Tuning | ForTune EUV (Ji HyeRim) | * Status: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung * Plan: Have customer feedback (Jan 23rd) Hold due to low ROI
SEC | Tuning | ForTune EUV (Ji HyeRim) | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week * Plan: ZEISS look into the result
SEC | Tuning | ForTune EUV (Ji HyeRim) | * Status: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
SEC | Tuning | ForTune EUV (Ji HyeRim) (DongHoon Koo) | * Status: Overcorrection from F601 process (Resolved issue) * Task : Figure out the reason of overcorrection (At the moment customer think mask bow from z height offset is the rootcause) * Action: HQ service engineer and SSC HW engineers figured out that there was offset  Offset calibration is done * Plan: Share the report to customer including feedback for customer questions
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Review the document between Samsung and HQ (change the input map for the CSR  Agreed between Samsung and ZEISS) • Plan: Have HQ feedback for flatness item (Schedule : TBD)
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does not support 2D jobs (2026-02-23) • Task : Need to discuss with customer on the information • Action: Talk to customer the situation and have background from customer do not use 3D jobs • Plan: Have a meeting with HQ on site to discuss this topic
SEC | Tuning | ForTune EUV | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung share required files • Plan: ZEISS perform the demo and discuss the outcome during HQ engineer on site visit(week of March 9th)
SEC | PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | * Status: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. * Plan: Fix the favor on scheduled date. (Plan: 2/06)
SEC | PROVE | neXT (SR1) (DongHoon, Koo) | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
SEC | PROVE | HR (DongHoon, Koo) (Kiwon, Cho) | * Status: The customer raised a question regarding the discrepancy observed between DB mode results (Correlation vs. Symmetry). * Task: Review the data and discuss the issue internally with HQ. * Action: Shared the customer’s data with HQ and initiated the technical discussion. * Result: Due to unavailability of additional measurements, further analysis cannot be performed at this stage. * Plan: No further investigation can be conducted for this case. We will inform the customer and propose to investigate similar cases proactively if the same issue occurs in further measurement
SEC | PROVE | neXT (DongHoon, Koo) | [TTTM] * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. * Plan: Monitor the progress of the master tool transition.
SEC | PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | [Hang-up] * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SEC | PROVE | neXT (N011) (P4) (DongHoon, Koo) | [SECS/GEM] - Status: Using Tool Independent Job in SECS/GEM. Global Option “Use tool specific Settings” = True, but remote batch runs produce error. * Task: Gather CSI an Job.xml files and request analysis to identify the error cause * Action: Requested CSI & Job file from Customer * Result: File requested completed * Plan: Once files are received , forward to Peter and monitor analysis
SEC | PROVE | Tool Dev. | * Customer Meeting : 9th Feb. Confirmed at K1 gate
SK hynix | Repair | LE #2 (Plan) | 1. LE#2 Source and ATP discussion. * Source inspection : 18th May ~ 20nd May 2026 * Attendance from SKH : 박인영 TL 2. NOCl only recipe request * Priority : Middle * Status : NOCl only shape request for particle removal. * Task / Action plan. a. SKH requests to provide NOCl only shapes for Particle removal - Under discussion in HQ - Target Completion : TBD
SK hynix | Repair | Auto Repair (with neXT & LE) | 1. Auto Repair Demo Request from Customer * Priority : High * Status : Auto Repair Demo from Oct 2025 at neXT and LE. * Task : Configuration set-up for Auto Repair Demo evaluation. * Action. a. Discussion for Auto Repair improvement roadmap items. - HQ will provide updated timeline for implementation of open items. --> Key function which need to be improvement until 2026 for AR purchasing in SKH. * neXT : Fine contour pattern copy (2Q 2026), * LE : Defect centering error : improved by parameter adjustment. - Target Completion : End of 2026 b. LE / neXT : Demo license for Auto Repair 3.0 & SimOp - Auto Repair 3.0 Demo evaluation with SimOp until end of June 2026 - SimOp installtion for neXT&LE will be completed on end of Feb 2026 * Plan - LE : Auto Repair success rate monitoring in production and SimOp set-up. - neXT : Auto Repair success rate monitoring in production and SimOp set-up
SK hynix | Repair | Tool Monitoring (with LE) | 1. Tool-monitoring (Sentinel & DataCenter) Demo evaluation on SKH * Priority : Low * Status : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Alignment with Customer for Tool-Monitoring Demo schedule. * Action : online demo and live evaluation on customer tool. * Plan : HQ will provide online demo first then if customer interesting.
SK hynix | Repair | High NA EUV PSM | 1. EUV PSM High-NA (Pt based) *Status : Pt based Hi-NA mask with Cr buffer is promising. *Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. *Action : Progress update to SKH for etch performance. *Plan : EUV PSM update meeting has been aligned on 20th March (Felix will visit SKH)
SK hynix | Repair | Monthly Technical meeting (General Issue) | 1. Application issue update meeting. * Date : 25th Feb. * Agenda : - Applicaion issue items list update.
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon, Cho) | [S/W upgrade - WLCD 0.5 Release] - Status: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | 1. [Application] - Phase offset investigation with AFM underway • Status: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Status: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attache VM with new. : OK (valide for root cause. Possible corruction of network) - Recovery attempt: Scheduled for Thursday
SK hynix | AIMS EUV | AIMS EUV 3.0 (Soonyoung Lee) | * Status: FF2 upgrade (CW04) * Task : FF2 upgrade (FAVOR upgrade for apps), Smoke tests * Action: FAVOR FF2 upgrade and verification planned on Wednesday/Thursday. * Result: FF2 upgrade completed, smoke test passed.
SK hynix | AIMS EUV | AIMS EUV 3.0 (Soonyoung Lee) | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search
SK hynix | AIMS EUV | AIMS EUV 3.0 (Soonyoung Lee) | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation
SK hynix | AIMS DUV | AAA (SoonYoung) | * Status: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
SK hynix | AIMS DUV | AAA (SoonYoung) | * Status: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
SK hynix | AIMS DUV | AIMS 1x (WonTae) | * Status: AIMS 1x TTTM * Task : Defect Size measured differently between AIMS 1x #4 & #6 * Action: HQ & SK Hynix had discussion for this topic * Result: According to Disar illumination from AIMS 1x #6, its intensity is not uniformity. * Plan: Created ticket for Escalating it to HQ. HQ apps engineer will be working on it. shared information with SSC service team. They are going to do troubleshooting once schedule is set up.
SK hynix | AIMS DUV | WLCD (WonTae) | [WLCD Publish Paper] * Status: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
SK hynix | AAA | AAA | * Status: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
SK hynix | AAA | AAA AIMS EUV | SK hyunix VoC 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
SK hynix | Tuning | ForTune EUV (HyeRim) | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Result: Ein m/o Feb * Plan: Have measurement result (registration & overlay) from customer | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT (DongHoon Koo) (HyeRim) | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. * Plan: After receiving the demo results from HQ, deliver the result to the customer for further evaluation
SK hynix | PROVE | PROVE neXT (DongHoon Koo) (KiWon) | * Status: A customer has inquired to have desired feature in PROVE. * Task : To have an introduction session for PROVE GUI * Result: Will be held in March at CJ office
SK hynix | PROVE | High Resolution (Dev) | * Customer Meeting : 10th Feb. Confirmed - the week of SEMICON Korea
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | 1. F-ATP completion : 22nd Jan. * ATP sign-off : Pending items discussion is on going (Target: in Feb.) - Pending items : AMX and AM modificaiton support. --> Under discussion with HQ.
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | * Status: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: ongoing (Visiting schedule in CW06)
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | • Status: Windows Korean patch • Task : to patch windows language pack in fab neo • Action: given .cab data was not successfully installed. • Result: requires turn-around solution

## CW09_New
Cus. | FoB | Tool | Title | Status | Next Plan | Reference (Internal If anything)
HQ | All | HQ visit |  |  | * 03/03 ~ 03/06 - AAA (Thomas Zuener) - SK hynix 3/3~3/4, Samsung 3/5 ~ 3/6 * 03/09 ~ 03/12 - Tuning in Samsung (Sami & Alex) : - 3/9: SSC training ¦ 3/10~3/11: Samsung Meeting with ForTune DUV & ForTune MLM * 03/18 ~ 03/20 - MeRiT EUV PSM discussion (Felix) : 3/19 : SSC on-site meeting ¦ 3/20 : SK Hynix on-site meeting.
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process set-up delay * Task: Compensation discussion for delay * Action: SSC has suggsted Gas sensor parts as compensation item. | * waiting for feedback from Samsung.
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] *Status: Min ESB signal fluctuation happens. but no impact in the tool operation. *Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. | * Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process set-up delay * Task: Compensation discussion for delay * Action: SSC has suggsted Gas sensor parts as compensation item. | * waiting for feedback from Samsung.
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation happens. but no impact in the tool operation. * Task: keeping stable ESB signal. * Action : Changed back to Samsung Video signal due to high Gap. | * Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade is required for SEC/GEM 300 bug fix * Task: SW upgrade and checking for SECS/GEM300 bug fix * Action: SW 5.6.0 has been released on 23th Feb. [RS4 contamination test] * Status: RS4 contamination with RS4 gas is required * Task: Samsung permission is needed for RS4 bottle open * Action : waiting Samsung's permission [Reduce backside particle (H/W)] * Status: Backside particle is observed on mask. * Task: Cleaning for mask handling system. * Action : HW action required | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW. | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade is required for SEC/GEM 300 bug fix * Task: SW upgrade and checking for SECS/GEM300 bug fix * Action: SW 5.6.0 has been released on 23th Feb. | * SSC will align tool time with Samsung for upgrade SW.
SEC | Repair | M50 neXT | Ch8 liquid water upgrade for SiN process | * Status: Samsung request an Upgrade of Ch8 from iced to liquid water. * Task: Special request: Ch8a with 40µm orifice and Ch8b 145µm orifice (Samsung standard) * Action: 1) ZEISS would provide the upgrade at SEC M50 tool to liquid water (s. request below) free of charge to Samsung. 2) SSC application team will support SiN process tuning, and Samsung will provide ZEISS protocol data for tunning. | * Priority of liquid water upgrade is low for Samsung. * SSC asked decision to Samsung, go or stop for liquid water upgrade.
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung will visit on HQ for AE demo on June 2026. * Task: Demo items alignment with Samsung is required. * Action: Demo items 1) Delta column performance evaluation 2) HNA EUV PSM evaluation on LE tool. | * Alignment meeting for Delta column demo items has been scheduled on 11st March. * Alignment meeting for HNA EUV PSM has been scheduled on 19th March (Felix will visit Samsung)
SEC | Repair | Auto Repair (with next) | Auto Repair 3.0 | * Status: AR evaluation and open items improvement. * Task: Auto Repair 3.0 Success rate (40%) collection. . * Action: 1) Sugguestion sing-off to customer 2) Open items discussion for close. | * SW 4.15.1 upgrade for Auto Repair improvement (for open items close) * Continue Auto Repair evaluation on neXT #1 ~ #4
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : 1) Improvement of selectivity up to 300% with new gas chemistry 2) Ta vs. Cr buffer layer etch performance with new gas chemistry. 3) New Gas candidate need to be informed to Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint is visible after EUV PSM etch process. * Task : Samsung and ZEISS collaboration work to find root case. * Action : ZEISS will start discussion to find root case. | [EUV PSM High-NA (Pt based)] * EUV PMS update meeting has been scheduled on 19th March (Felix will visit Samsung) [EUV PSM Mesh imprint issue on neXT and LE] * Samsung will provide ZEISS relevant data for Mesh imprint issue.
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentienl & Datacenter) | * Status : Tool-monitroing improvement is on-going * Task : Sentinel & Datacenter SW upgrade as following roadmap * Action : Sentinel 1.6 version / DataCenter 1.1 version upgrade | * Align Tooltime with Samsung for upgrade 1.6 / 1.1 of MeRiT Tool Monitoring Sentinel / DataCenter.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Setup FAVOR at P2 data center. tool S/W upgrade will be followed up. * Task: Make communication between P2 and NRD. * Action: SEC plan to check for above. | 1) Timeline has been shared to Samsung and, wish to revise as staring after Lunar New year. CW09 ~ CW10 for on-site work | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | AIMS EUV 1.0 Mask Alignment Investigation | [Mask Alignment Failure] * Status: AIMS EUV 1.0 Mask Alignment Failure * Task : Investigate AIMS EUV 1.0 alignment fail * Result: POA applicable after - A. Better description of VIS-EUV offset setting relationship - B. Increasing counts of spiral search in VIS and EUV alignment
SEC | AAA | AAA EUV (P4) (Cho, KiWon) | AAA Software Installation Preparation | * Status: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feeeback (2025-12-29) * Result: N/A
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) |  | - Status: No communication to CCD afte * fi *mwa *e *ollback - AT(Acceptance Test) afte * CCD came *a *eplacement - Task : To *un sho *t AT afte * CCD *eplacement since it has ente *ed the vacuum chambe * that impacts measu *ement. - Action: 13 hou *s of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - *esult: Satisfy p *evious AT spec ta *get.
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | Monitoring Batch Clear Position Investigation | * Status: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document Sharing for Phase Metrology and WLCD | * NDA Document received from Samsung in 17th, Nov (Dr. Roh) Stauts: NDA being shared to SEC (Dec 1st) 1. Subject: Phase Metrology with Demo Scope - Demo : September timeline 2. Subject: WLCD EUV feasibility check * Task: precise measurement in Phase Metrology and WLCD
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Classification Code Saving Request | • Status: Save classification code when using rff. (1/25) • Task : Customer request that classification code has to be seen in result files when using rff files. • Action: NA • Result: NA | • Plan: Need to narrow down which tool/customer first.
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | AIMSHOST Error Investigation | • Status: AIMSHOST-Error _ unhandled exception • Task: SECS GEM bug investigation required. • Action: Open sustaining ticket for this issue. • Result: NA. | • Plan: Log export handled by HW team.
SEC | AIMS DUV | AIMS 1x (SR1) | AIMS 1x Intensity Difference Improvement | • Status: AIMS 1x in SR1 have an Intensity Difference. • Task : AIMS 1x TTTM. Need to Improve diff. image. • Action: H/W team provided correction activity in CW46. • Result: Good before MAA cal. Not Good: After MAA cal. | • Plan: H/W team is checking with HQ whether MAA need to be replaced.
SEC | AIMS DUV | AIMS 1x (NRD) | AIMS 1x SW Upgrade to Version 6.18.3 | • Status: AIMS 1x 6.18.2 SW need to be upgrade. • Task: SW upgrade • Action: NA • Result: No upgrade items found in ftp. | • Plan: Target SW ver is changed to 6.18.3. waiting for releasing target version | 2. AIMS 1x tool SW Upgrade Ver. 6.15 1) Done SW Upgrade for both NRD and SR1 2) Plan to upgrade SW for Fab Neo with 1.17 (20th March)
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA Service App Running Failure Investigation | * Status: AAA Service app running failure after reboot linked with AIMS 1x tools * Task : Fix AAA Service star sequence to normal * Action: Test with removing IP address from CodeMeter configuration and re-start AAA service with plugging. * Result: Failure with removing IP address from CodeMeter | * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve]
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA SW 2.33 Upgrade Completion | * Status: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading | * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation)
SEC | AAA | AAA with automation | AAA Analysis Failure with Monitoring Lot | * Status: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Task : Customer Extended ROI length. * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. | * Plan: plan to discussion it at Bi-weekly Application call 09/29 (cancelled) *> Next call (10/28) * New POA: Suggest Create New recipe and share exported new recipe to HQ
SEC | AAA | AAA FAVOR(P4) (WonTae) (KiWon) | P4 AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Task : Difficulty to figure out Defect # and position identification * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | * Plan : Request HQ to review the P4 AAA RNR defect numbering logic and provide a fix
SEC | AAA | AAA FAVOR(P4) (WonTae) | P4 FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Task : Matlab Error with process failure when multiple process is running * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. Escalated it to HQ | * Plan : The log including abnormal event to HQ. will investigate it.
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Send some question about FTM and job automation to HQ (Feb 4th) | • Plan: Waiting for HQ feedback for the Gantt chart & answers for the questions + discuss it during HQ on site visit on week 11
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (week of 15th Feb) • Action: PW has been obtained with blank 2 | • Plan: It is delayed due to mask export issue. Once we fixe it, restart the process
| Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | PIP Blank 8 Mask Process Correction | Task: PIP Blank 8 (CDC EUV after RegC) : Israel Status: Blank 8 mask process (2nd RegC after EUV CDC) Task : HQ perform 2nd RegC after EUV CDC at HQ side Action: Figured out there was human error during RegC process | Plan: Redo the process
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: Perform the process (done) + The mask is coming back to Korea | • Plan: Once the mask is arrived in Korea, customer measure the results
SEC | Tuning | ForTune MLM (HyeRim) | HVM Tool Introduction Slides | • Situation: HVM tool introduction slides • Task : To share HVM tool introduction slides • Action: Ask to HQ to share the prepare the slides | • Plan: ZEISS shared the slides to Samsung Feb 12th
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : b/o March)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled by b/o Feb)
SEC | Tuning | ForTune MLM (Kim, WonTae) | PIP Activity and Wafer Evaluation | * Status: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it.
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Feedback | * Status: SECS GEM 300 Application part * Task : Job creation automation preparation * Action: Send Gantt chart regarding automation / HW / Application items to HQ (Jan 20th) | * Plan: Waiting for HQ feedback for the Gantt chart * Support needed : Schedule for FTM ready is required ASAP to discuss job automation
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) | * Plan: RegC : Aligned between ZEISS and Samsung for the new feature required for automation  New FTM need to be released CDC : Customer request was shared to HQ but rule is not clear for HQ  To share clear rule that samsung required
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Wait for HQ feedback
SEC | Tuning | ForTune EUV (Ji HyeRim) | New BSC Material Mask Process Setup | * Status: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung | * Plan: Have customer feedback (Jan 23rd) Hold due to low ROI
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include rootcause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week | * Plan: ZEISS look into the result
SEC | Tuning | ForTune EUV (Ji HyeRim) | Simulation Result Discrepancy Investigation | * Status: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. | * Plan: Samsung performed 2nd RegC at E601 and see the results looks okay
SEC | Tuning | ForTune EUV (Ji HyeRim) (DongHoon Koo) | Overcorrection Issue Resolution | * Status: Overcorrection from F601 process (Resolved issue) * Task : Figure out the reason of overcorrection (At the moment customer think mask bow from z height offset is the rootcause) * Action: HQ service engineer and SSC HW engineers figured out that there was offset  Offset calibration is done | * Plan: Share the report to customer including feedback for customer questions
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 CSR Document Review | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Review the document between Samsung and HQ (change the input map for the CSR  Agreed between Samsung and ZEISS) | • Plan: Have HQ feedback for flatness item (Schedule : TBD)
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does not support 2D jobs (2026-02-23) • Task : Need to discuss with customer on the information • Action: Talk to customer the situation and have background from customer do not use 3D jobs | • Plan: Have a meeting with HQ on site to discuss this topic
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung share required files | • Plan: ZEISS perform the demo and discuss the outcome during HQ engineer on site visit(week of March 9th)
SEC | PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | LRM feature enablement | * Status: Customer inquired about the possibility of using the LRM fuction * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. | * Plan: Fix the favor on scheduled date. (Plan: 2/06)
SEC | PROVE | neXT (SR1) (DongHoon, Koo) | In-cell measurement Investigation | * Status: The customer reported that the In-cell measurement results were out of spec. (CW50) * Task: Figure out the root cause. * Action: Discussion back and forth Created the ticket, delivered the data to HQ, and discussed the issue in the Application Call. * Result: HQ requested additional measurement to verify Accuracy with new “ROI” settinge | * Plan: Customer will measure in-cell pattern with new “ROI” setting within January.
SEC | PROVE | neXT (DongHoon, Koo) | TTTM transition to PROVE neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | * Plan: Monitor the progress of the master tool transition.
SEC | PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Source mask sending to HQ. | * Additional EUV PSM mask will be sended to HQ.
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evalution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evalution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error need to be fixed [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evalution on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March [Auto Repair 3.0 evaluation on LE] * Defect centering test [Auto Repair SimOp evaluation] * Trouble shooting and set-up
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentienl & Datacenter) | * Status : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : If customer satisfy online demo then move to live evaluation on tool. | * Waiting for Auto Repair 3.0 evaluation completion.
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with new gas chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Pt based Hi-NA mask with Cr buffer is promising. * Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. * Action : HQ progress update to SKH for etch performance. | [EUV PSM (Ru based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) [EUV PSM High-NA (Pt based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH)
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon, Cho) | WLCD 0.5 Software Upgrade Requirement | [S/W upgrade - WLCD 0.5 Release] - Status: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) |  | 1. [Application] - Phase offset investigation with AFM underway • Status: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Status: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A |  | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM Recovery Attempt | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attache VM with new. : OK (valide for root cause. Possible corruction of network) | Recovery attempt: Scheduled for Thursday
SK hynix | AIMS EUV | AIMS EUV 3.0 (Soonyoung Lee) | FF2 Upgrade and Smoke Test Completion | * Status: FF2 upgrade (CW04) * Task : FF2 upgrade (FAVOR upgrade for apps), Smoke tests * Action: FAVOR FF2 upgrade and verification planned on Wednesday/Thursday. * Result: FF2 upgrade completed, smoke test passed.
SK hynix | AIMS EUV | AIMS EUV 3.0 (Soonyoung Lee) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search
SK hynix | AIMS EUV | AIMS EUV 3.0 (Soonyoung Lee) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation
SK hynix | AIMS DUV | AAA (SoonYoung) | RnR File Removal Investigation | * Status: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result:
SK hynix | AIMS DUV | AAA (SoonYoung) | AAA RnR File Opening Issue | * Status: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending.
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: AIMS 1x TTTM * Task : Defect Size measured differently between AIMS 1x #4 & #6 * Action: HQ & SK Hynix had discussion for this topic * Result: According to Disar illumination from AIMS 1x #6, its intensity is not uniformity. | * Plan: Created ticket for Escalating it to HQ. HQ apps engineer will be working on it. shared information with SSC service team. They are going to do troubleshooting once schedule is set up.
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: WLCD Measurement for BACUS 2026 publication * Task : Prepare publish paper at BACUS 2026. * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible | * Plan: will do evaluation on another feature (CH analysis, Min Cd analysis End-End feature, EvalCD analysis) and preparing abstract
SK hynix | AAA | AAA | AAA 2.33 Upgrade Installation Failure | * Status: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. | * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04)
SK hynix | AAA | AAA AIMS EUV | SK Hynix VoC Updates | 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch.
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Result: Ein m/o Feb | * Plan: Have measurement result (registration & overlay) from customer | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT (DongHoon Koo) (HyeRim) | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation
SK hynix | PROVE | PROVE neXT (DongHoon Koo) (KiWon) | Intro session for PROVE GUI | * Status: A customer has inquired to have desired feature in PROVE. * Action : To have an introduction session for PROVE GUI * Result: | Session will be held in March
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP compeletion on 22nd Jan * Task : Align pending items and ZEISS recipe supprot with Tekscend * Action: AMX and AM modificaiton support discussion | * Waiting for decision from HQ for recipe supprot
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | Long Term CD Dynamic Repeat Test Guideline Suggestion | * Status: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: ongoing (Visiting schedule in CW06)
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | Windows Korean Patch Installation Issue | • Status: Windows Korean patch • Task : to patch windows language pack in fab neo • Action: given .cab data was not successfully installed. • Result: requires turn-around solution

## CW10
Cus. | FoB | Tool | Title | Status | Next Plan |  | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support | * 03/03 ~ 03/06 - AAA (Thomas Zuener) - SK hynix 3/3~3/4, Samsung 3/5 ~ 3/6 * FAOVR Engineer: For DFI & FAVOR with PROVE in SR1 (Sven Schutze, Tino Kaiser, Katja Notarangelo) | * 03/09 ~ 03/12 - Tuning in Samsung (Sami & Alex) : Cancelled - SSC training, SEC Meeting (ForTune DUV & ForTune MLM) * 03/18 ~ 03/20 - MeRiT EUV PSM discussion (Felix) : SEC & SK Hynix meeting.
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026)
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.0 released on Feb 23 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW. |  | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.0 released on Feb 23 | * SSC will align tool time with Samsung for upgrade SW.
SEC | Repair | M50 neXT | Ch8 liquid water upgrade for SiN process | * Status: Samsung requested an upgrade of Ch8 from iced water to liquid water * Task: Special request for Ch8a with 40 µm orifice and Ch8b with 145 µm orifice (Samsung standard) * Action: 1) ZEISS to provide free upgrade to liquid water at the SEC M50 tool 2) SSC application team to support SiN process tuning; Samsung to provide ZEISS with protocol data for tuning | * Priority of liquid water upgrade is low for Samsung. * SSC asked decision to Samsung, go or stop for liquid water upgrade.
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation 2) HNA EUV PSM evaluation on LE tool. | * Alignment meeting for Delta column demo items has been scheduled on 11st March. * Alignment meeting for HNA EUV PSM has been scheduled on 19th March (Felix will visit Samsung)
SEC | Repair | Auto Repair (with next) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.1 upgrade for Auto Repair improvement (for open items close) * Continue Auto Repair evaluation on neXT #1 ~ #4
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : 1) Improvement of selectivity up to 300% with new gas chemistry 2) Ta vs. Cr buffer layer etch performance with new gas chemistry. 3) New Gas candidate need to be informed to Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : ZEISS to initiate discussions to find the root cause | [EUV PSM High-NA (Pt based)] * EUV PMS update meeting has been scheduled on 19th March (Felix will visit Samsung) [EUV PSM Mesh imprint issue on neXT and LE] * Samsung will provide ZEISS relevant data for Mesh imprint issue.
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : Upgrade to Sentinel v1.6 and DataCenter v1.1 | * Align Tool time with Samsung for upgrade 1.6 / 1.1 of MeRiT Tool Monitoring Sentinel / DataCenter.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: Configured and Powered up the network functionality - System powered up (using two cables) - Samsung completed mandatory security - Windows Server 2022 OS licenses authenticated (all 10 VMs) - Favor team performed resource checks - Samsung Data Center assigned network - Internal clustering ongoing (3 server hosts, 2 switches) | * Tool S/W upgrade will be followed up by March |  | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | DFI Upgrade 후에 Log monitoring 후에 event 증가하면 조율 예정 | Done
SEC | AAA | AAA EUV (P4) (Cho, KiWon) | AAA Software Installation Preparation | * Status: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feedback (2025-12-29) * Result: N/A
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) |  |  | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) | Monitoring Batch Clear Position Investigation | * Status: Wrong clear position for monitoring batch (CW03) * Task: Investigate batch for any mistakes for clear position * Action: under investigation, no error to be seen. * Result: Customer mask had wrong clear position, Case close. | completed. Customer mistook mask fabrication. | Done
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | Status: NDA under reviewing by SEC (CW08) * Subject: Phase Metrology & WLCD EUV * Task: precise measurement in Phase Metrology and WLCD | * Estimated review completion mid of March
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Classification Code Saving Request | • Status: Save classification code when using rff. (1/25) • Task : Customer request that classification code has to be seen in result files when using rff files. • Action: NA • Result: NA | • Plan: Need to narrow down which tool/customer first. | Done
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | AIMSHOST Error Investigation | • Status: AIMSHOST-Error _ unhandled exception • Task: SECS GEM bug investigation required. • Action: Open sustaining ticket for this issue. • Result: NA. | • Plan: Log export handled by HW team. | Done
SEC | AIMS DUV | AIMS 1x (SR1) | AIMS 1x Intensity Difference Improvement | • Status: AIMS 1x in SR1 have an Intensity Difference. • Action: H/W team provided correction activity in CW46. • Result: Good before MAA cal. Not Good: After MAA cal. | Currently, No issue with Different intensity. Monitoring | Done
SEC | AIMS DUV | AIMS 1x (NRD) | AIMS 1x SW Upgrade to Version 6.18.3 | • Status: AIMS 1x 6.18.2 SW need to be upgrade. • Action: NA • Result: No upgrade items found in ftp. | All requirement for SW upgrade was submitted through Azure. HQ is going to check and share Target SW version
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA Service App Running Failure Investigation | * Status: AAA Service app fails to run after reboot when linked with AIMS 1x tools * Action: est performed by removing IP address from CodeMeter configuration and restarting AAA Service with dongle plugged in * Result: Issue not resolved; failure persists after removing IP address from CodeMeter configuration | * Plan: plan to discussion it at Bi-weekly Application call (09/16) [NO ACTION ITEM & PLAN: Seems No idea how to solve] | Done
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA SW 2.33 Upgrade Completion | * Status: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading | * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation) | Done
SEC | AAA | AAA with automation | AAA Analysis Failure with Monitoring Lot | * Status: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. | New POA: Suggest Create New recipe and share exported new recipe to HQ
SEC | AAA | AAA FAVOR(P4) (WonTae) (KiWon) | P4 AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | Will discuss it next Thursday during Thomas Korea Visit Same issue happened at SK hynix FAVOR 3.1 Merged it with SK hynix case
SEC | AAA | AAA FAVOR(P4) (WonTae) | P4 FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. Escalated it to HQ | Will discuss it during Thomas Korea visit
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Send some question about FTM and job automation to HQ (Feb 4th) | • Plan: Waiting for HQ feedback for the Gantt chart & answers for the questions + discuss it during HQ on site visit on week 11 |  | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (Schedule : TBD) • Action: PW has been obtained with blank 2 & 2 blanks were sent to Israel in advance | • Plan: It is delayed due to mask export issue. Once we fix it, restart the process
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | PIP Blank 8 Mask Process Correction | Task: PIP Blank 8 (CDC EUV after RegC) : Israel Status: Blank 8 mask process (2nd RegC after EUV CDC) Task : HQ perform 2nd RegC after EUV CDC at HQ side Action: Figured out there was human error during RegC process | Plan: Redo the process | Done
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: Perform the process (done) + The mask is under measurement at Samsung | • Plan: Once customer share the data, HQ prepare the report
SEC | Tuning | ForTune MLM (HyeRim) | HVM Tool Introduction Slides | • Situation: HVM tool introduction slides • Task : To share HVM tool introduction slides • Action: Ask to HQ to share the prepare the slides | Completed | Done
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD
SEC | Tuning | ForTune MLM (Kim, WonTae) | PIP Activity and Wafer Evaluation | * Status: PIP (Product Improvement Project) activity 2. Task: Laser Tune & Test mask 3ea * Action: Patterned & PIP Blank 4 was shipped on 08/04 * Action: PIP Blank3 needs EUVR Measurement. to be shipped on 9/09 *> PIP Blank3 shipped on 09.09 * Action: Mask layout will be shared by Samsung (08/12) 3. Task: Wafer Evaluation 1 * Action: After process in Israel, mask returned to Samsung * Action: Due to Samsung Tool statement, it is delayed. (AIMS EUV Tool availability) * Action: Waiting for Wafer test result from Photo team 4. Task: Wafer Evaluation 2 * Action: Due to Samsung Tool statement, it is delayed. * Action: Delaying AIMS EUV data based on CD  Grizelda will handle it (09/16) * Pending Item * Task: Bi-layer process set up support schedule in Samsung on F-EUV tool: CW30 (7/23 ~ 7/25) * Action: HQ will share procedure and service team will work on it. |  | Done
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Have a meeting with customer to discuss how they deal with jobs and script * Action: Make HQ understand how customer deal with jobs and script (RegC) : Done on Oct 27th / Share automation script format to customer (CDC) | * Plan: RegC : Aligned between ZEISS and Samsung for the new feature required for automation  New FTM need to be released CDC : Customer request was shared to HQ but rule is not clear for HQ  To share clear rule that Samsung required
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Wait for HQ feedback
SEC | Tuning | ForTune EUV (Ji HyeRim) | New BSC Material Mask Process Setup | * Status: New BSC material mask process setup * Task : Follow up to process setup for new BSC material mask * Action: Share Gantt chart including to process blank A&B to Samsung | * Plan: Have customer feedback (Jan 23rd) Hold due to low ROI
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week | * Plan: ZEISS look into the result
SEC | Tuning | ForTune EUV (Ji HyeRim) | Simulation Result Discrepancy Investigation | * Status: 1) The Simulation result for 2 bottom modes is different from the expected value 2) Samsung expected the RegC simulation result to be close to zero, but it shows around 0.8. 3) After CDC, Samsung performed a 2 bottom modes simulation for the 2nd RegC, but the result was not as expected. * Task: Identify why the 2nd correction shows a value that deviates from expectations. * Action: 1) Confirmed that the flatness map input is required for the simulation. 2) Investigate the root cause of the unexpected result in the 2nd correction. | Completed | Done
SEC | Tuning | ForTune EUV (Ji HyeRim) (DongHoon Koo) | Overcorrection Issue Resolution | * Status: Overcorrection from F601 process (Resolved issue) * Task : Figure out the reason of overcorrection (At the moment customer think mask bow from z height offset is the root cause) * Action: HQ service engineer and SSC HW engineers figured out that there was offset  Offset calibration is done | * Plan: Share the report to customer including feedback for customer questions | Done
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 CSR Document Review | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Have a final version of the document on March 3rd | • Plan: Have HQ feedback for final version by this week
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does not support 2D jobs (2026-02-23) • Task : Need to discuss with customer on the information • Action: Talk to customer the situation and have background from customer do not use 3D jobs | • Plan: Have a meeting with HQ on site to discuss this topic • Plan: Have a technical slides that explain ForTune DUV #2 (F312) SECS GEM 300 does not support 2D jobs
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung share required files | • Plan: ZEISS perform the demo and discuss the outcome during HQ engineer on site visit(week of March 9th)
SEC | PROVE | neXT (SR1) (DongHoon, Koo) (KiWon, Cho) | LRM feature enablement | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Need to schedule with HQ to fix a FAVOR on SR1 PROVE tool * Result: Schedule with a customer to get a tool time for fixing the FAVOR in February. | * Plan: Fix the favor on scheduled date. (Plan: 2/06)
SEC | PROVE | PROVE | In-cell measurement out of spec | Subject: Analyze if correlation mode cause registration offset Action: Correlation quality check is done , which was fine. Result: Request incell accuracy measurement | Waiting for Incell accuracy result from customer
SEC | PROVE | neXT (DongHoon, Koo) | TTTM transition to PROVE neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | * Plan: Monitor the progress of the master tool transition.
SEC | PROVE | PROVE next ( P4 ) | SW upgrade for Automation patch | Subject: SW upgrade required to install automation patch ( 4.15.1 -> 4.16 ) Action: Collect config files from the tool Result: | Request SW package from peter
SEC | PROVE | PROVE next ( SR1 ) | FAVOR 3.0 enablement for RS2.0 | Subject: To enable RS2.0, FAVOR must be connected to PC Action: Investigated the failure case of FAVOR Result: FAVOR need to be fixed with HQ engineer | Wait for HQ engineer visit
SEC | PROVE | PROVE | High-Performance mode demo | Subject: Customer want to evaluate HPM demo’s resolution Action: Set up the schedule for demo Result: Demo mask will be delivered. | Wait for Demo mask delivery from SEC.
SEC | PROVE | HR (NRD) (DongHoon, Koo) (KiWon, Cho) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Source mask sending to HQ. | * Additional EUV PSM mask will be sent to HQ.
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error need to be fixed [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March [Auto Repair 3.0 evaluation on LE] * Defect centering test [Auto Repair SimOp evaluation] * Trouble shooting and set-up
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : If customer satisfy online demo then move to live evaluation on tool. | * Waiting for Auto Repair 3.0 evaluation completion.
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with new gas chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Pt based Hi-NA mask with Cr buffer is promising. * Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. * Action : HQ progress update to SKH for etch performance. | [EUV PSM (Ru based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) [EUV PSM High-NA (Pt based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH)
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon, Cho) | WLCD 0.5 Software Upgrade Requirement | [S/W upgrade - WLCD 0.5 Release] - Status: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) |  |  | 1. [Application] - Phase offset investigation with AFM underway • Status: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Status: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A |  |  | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM Recovery Attempt | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attach VM with new. : OK (valued for root cause. Possible corruption of network) | Recovery attempt: Scheduled for Thursday
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | FF2 Upgrade and Smoke Test Completion | * Status: FF2 upgrade (CW04) * Task : FF2 upgrade (FAVOR upgrade for apps), Smoke tests * Action: FAVOR FF2 upgrade and verification planned on Wednesday/Thursday. * Result: FF2 upgrade completed, smoke test passed. | Completed | Done
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * will work during bore swap schedule.
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation | * waiting from HQ updates.
SK hynix | AIMS DUV | AAA (SoonYoung) | RnR File Removal Investigation | * Status: All RnR File has been removed without intention once SECS/GEM200 activated. Customer explained. * Task: Figure out root cause. * Action: Gathered Windows event logs 1) Gathered Windows event logs 2) test again with automation turned ON. * Result: |  | Done
SK hynix | AIMS DUV | AAA (SoonYoung) | AAA RnR File Opening Issue | * Status: AAA cannot open RnR file (12/08) - Network disconnect when Big volume RnR file was loaded (5>) * Task: To give POA for current issue. (Frequency: Occasionally) * Action: map_share file and path location has to be shared with HQ (contains customer security information) * Result: HQ analysis pending. |  | Done
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: AIMS 1x TTTM * Action: HQ & SK Hynix had discussion for this topic * Result: According to Disar illumination from AIMS 1x #6, its intensity is not uniformity. | Service team have done Trouble shooting on AIMS 1x #6 - Pole Balance : 0.5% - Coma : 0.5% - Issued Defect tool setting Pupil intensity : Uniform SK hynix Process team will confirm tool status.
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible Remaining uncertainties Difference between CDx and CDy currently not explainable Unusual high mask CDU | Further investigations needed - set up meeting with HQ for further discussion at middle of march
SK hynix | AAA | AAA | AAA 2.33 Upgrade Installation Failure | * Status: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. | * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04) | Done
SK hynix | AAA | AAA AIMS EUV | SK Hynix VoC Updates | 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch. | Follow up with "Samsung Case colum 27"
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Result: Ein m/o Feb | * Plan: Have measurement result (registration & overlay) from customer |  | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT (DongHoon Koo) (HyeRim) | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation
SK hynix | PROVE | PROVE neXT (DongHoon Koo) (KiWon) | Intro session for PROVE GUI | * Status: A customer has inquired to have desired feature in PROVE. * Action : To have an introduction session for PROVE GUI * Result: | Session will be held in March
SK hynix | PROVE | PROVE neXT (DongHoon Koo) | Box/ Stamp Demo | Status: Database file and mask are prepared. Plan: Waiting for mask measurement |  | 1
SK hynix | PROVE | PROVE neXT (DongHoon Koo) | Box/ Stamp Demo | Subject: New clip file request for Demo. Action: Request to Hynix to get a bigger clip file Result: Bigger clip file is delivered to HQ | Process the measurement with new Clip file | 1
SK hynix | PROVE | PROVE neXT (DongHoon Koo) | FAVOR configuration check | Subject: Check the FAVOR configuration Action: Create a ticket to get a confirmation from Sabine Result: | Waiting for feedback | 1
SK hynix | PROVE | PROVE neXT (DongHoon Koo) | EUV mask requirement for ATP | Subject: Customer need to prepare EUV mask for ATP Action: Request to Sabine regarding spec of EUV mask during ATP Result: | Waiting for feedback | 1
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP compeletion on 22nd Jan * Task : Align pending items and ZEISS recipe supprot with Tekscend * Action: AMX and AM modificaiton support discussion | * Waiting for decision from HQ for recipe supprot
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | Long Term CD Dynamic Repeat Test Guideline Suggestion | * Status: Long term CD dynamic repeat test guide * Task : To suggest guideline for long term cd dynamic repeat test * Action: HQ did give answer related to it, but since Zeiss has no guideline for it, we neither can provide * Result: ongoing (Visiting schedule in CW06) |  | Done
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | Windows Korean Patch Installation Issue | • Status: Windows Korean patch • Task : to patch windows language pack in fab neo • Action: given .cab data was not successfully installed. • Result: requires turn-around solution |  | Done

## CW11
Cus. | FoB | Tool | Title | Status | Next Plan |  | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support | * ( ~ 3/11 ) - FAVOR on site support : Tthe FAVOR for DFI & FAVOR for PROVE in SR1 (Sven Schutze, Tino Kaiser, Katja Notarangelo) | * 03/18 ~ 03/20 : MeRiT EUV PSM discussion (Felix) - SEC & SK Hynix meeting. | 3_10
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026)
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.0 released on Feb 23 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW. |  | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.0 released on Feb 23 | * SSC will align tool time with Samsung for upgrade SW.
SEC | Repair | M50 neXT | Ch8 liquid water upgrade for SiN process | * Status: Samsung requested an upgrade of Ch8 from iced water to liquid water * Task: Special request for Ch8a with 40 µm orifice and Ch8b with 145 µm orifice (Samsung standard) * Action: 1) ZEISS to provide free upgrade to liquid water at the SEC M50 tool 2) SSC application team to support SiN process tuning; Samsung to provide ZEISS with protocol data for tuning | * Priority of liquid water upgrade is low for Samsung. * SSC asked decision to Samsung, go or stop for liquid water upgrade.
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation 2) HNA EUV PSM evaluation on LE tool. | * Alignment meeting for Delta column demo items has been scheduled on 11st March. * Alignment meeting for HNA EUV PSM has been scheduled on 19th March (Felix will visit Samsung) | 3_10
SEC | Repair | Auto Repair (with next) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.1 upgrade for Auto Repair improvement (for open items close) * Continue Auto Repair evaluation on neXT #1 ~ #4
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : 1) Improvement of selectivity up to 300% with new gas chemistry 2) Ta vs. Cr buffer layer etch performance with new gas chemistry. 3) New Gas candidate need to be informed to Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : ZEISS to initiate discussions to find the root cause | [EUV PSM High-NA (Pt based)] * EUV PMS update meeting has been scheduled on 19th March (Felix will visit Samsung) [EUV PSM Mesh imprint issue on neXT and LE] * Samsung will provide ZEISS relevant data for Mesh imprint issue.
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : Upgrade to Sentinel v1.6 and DataCenter v1.1 | * Align Tool time with Samsung for upgrade 1.6 / 1.1 of MeRiT Tool Monitoring Sentinel / DataCenter.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: Configured and Powered up the network functionality - System powered up (using two cables) - Samsung completed mandatory security - Windows Server 2022 OS licenses authenticated (all 10 VMs) - Favor team performed resource checks - Samsung Data Center assigned network - Internal clustering done (3 server hosts, 2 switches) - Share storage increased to 10TB - Configured settings to fulfill Samsung security rules - Drilling on FAVOR for DFI completed | * Tool S/W upgrade will be followed up by March | 3_10 | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | DFI Upgrade 후에 Log monitoring 후에 event 증가하면 조율 예정
SEC | AAA | AAA EUV (P4) (Cho, KiWon) | AAA Software Installation Preparation | * Status: Need to prepare AAA S/W install before HQ shutdown from next week (HVM target start: 5th Jan 2026) * Task: Encrytor error occurred. (2025-12-28) * Action: Reported to HQ and awaiting feedback (2025-12-29) * Result: N/A
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) |  |  | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | Status: NDA under reviewing by SEC (CW08) * Subject: Phase Metrology & WLCD EUV * Task: precise measurement in Phase Metrology and WLCD | * Estimated review completion mid of March
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Defect numbering mismatch | • Status: Defect numbering mismatch • Task: understand customer's automation workflow. • Action: short meeting with customer needed • Result: NA | • Plan: short meeting with customer | 3_10
SEC | AIMS DUV | AIMS 1x (NRD) | AIMS 1x SW Upgrade to Version 6.18.3 | • Status: AIMS 1x 6.18.2 SW need to be upgrade. • Action: NA • Result: No upgrade items found in ftp. | All requirement for SW upgrade was submitted through Azure. HQ is going to check and share Target SW version
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA SW 2.33 Upgrade Completion | * Status: AAA 2.33 upgrade * Task : AAA SW 2.33 upgrade at Samsung * Action: Upgrading AAA SW 2.33 for 3Q * Result: Completed AAA SW 2.33 Upgrading | * Plan: Aligning SW upgrade schedule after holiday SW release. (F/U will be placed after SK hynix installation) 설치 실패. RnR Job loading failure (CW10)
SEC | AAA | AAA with automation | AAA Analysis Failure with Monitoring Lot | * Status: AAA analysis Failure with Monitoring lot (DUV Only) (5/28 ~ ) * Action: Demonstrate the symptom for Developer to check it during meeting (9/03) * Result: HQ Developer & App engineer confirmed the symptom and what the problem is. | New POA: Suggest Create New recipe and share exported new recipe to HQ
SEC | AAA | AAA FAVOR(P4) (WonTae) (KiWon) | P4 AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | Will discuss it next Thursday during Thomas Korea Visit Same issue happened at SK hynix FAVOR 3.1 Merged it with SK hynix case
SEC | AAA | AAA FAVOR(P4) (WonTae) | P4 FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. Escalated it to HQ | Will discuss it during Thomas Korea visit
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Send some question about FTM and job automation to HQ (Feb 4th) | • Plan: Waiting for HQ feedback for the Gantt chart & answers for the questions + discuss it with HQ online on week of #12 | 3_10 key | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (Schedule : TBD) • Action: PW has been obtained with blank 2 & 2 blanks were sent to Israel in advance | • Plan: It is delayed due to mask export issue. Once we fix it, restart the process
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: Perform the process (done) + The mask is under measurement at Samsung | • Plan: Once customer share the data, HQ prepare the report
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Need a clear understanding of DAT file rule of checking. * Action: History: HQ understand how customer deal with jobs and script (RegC) - Done on Oct 27th - Share automation script format to customer (CDC) | * Plan: RegC : waiting FTM S/W roll out. (Aligned ZEISS and Samsung for the new feature required for automation) CDC : Customer request was shared to HQ but rule is not clear for HQ  To share clear rule that Samsung required | 3_10 Esc
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Postpone resolving the issue for now since full automation is not yet supported. After installing F312 and completing the full automation tests there, we will upgrade F306 to the same version and address this issue if it still persists | 3_10 key
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week | * Plan: ZEISS look into the result
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 CSR Document Review | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Have a final version of the document on March 3rd | Completed
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does NOT support 2D jobs (2026-02-23) • Task : Need to use 3D. Due to limitation of SECS GEM 300. Not Support. • Action: Talk to customer the situation and have background from customer do not use 3D jobs | • Plan: Have a meeting with HQ on site to discuss this topic • Plan: Have a technical slides that explain ForTune DUV #2 (F312) SECS GEM 300 does not support 2D jobs | 3_10 Esc
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung share required files | • Plan: ZEISS perform the demo and discuss the outcome during HQ engineer on site visit(week of March 9th)
SEC | Tuning | ForTune MLM | Shipment schedule | • Situation: ForTune MLM shipment schedule • Task : To check Backup plan with current HQ situation • Action: To check Backup plan with current HQ situation | • Plan: To check Backup plan with current HQ situation including Semi S2 Certification | 3_10 Esc
SEC | PROVE | PROVE neXT (SR1) | LRM feature enablement | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Investigate FAVOR3.0 with HQ engineers * Result: FAVOR3.0 seems fine, but PROVE still couldn't connect to FAVOR3.0 | * Plan: Discuss with HQ regarding PROVE connection | 3_10
SEC | PROVE | PROVE | In-cell measurement out of spec | Subject: Analyze if correlation mode cause registration offset Action: Correlation quality check is done , which was fine. Result: Request incell accuracy measurement | Waiting for Incell accuracy result from customer
SEC | PROVE | PROVE | TTTM transition to PROVE neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | Monitor the progress of the master tool transition.
SEC | PROVE | PROVE next ( P4 ) | SW upgrade for Automation patch | Subject: SW upgrade required to install automation patch ( 4.15.1 -> 4.16 ) Action: Collect config files from the tool Result: | Waiting for SW package prepared | 3_10
SEC | PROVE | PROVE | High-Performance mode demo | Subject: Customer want to evaluate HPM demo’s resolution Action: Set up the schedule for demo Result: Demo mask will be delivered. | Wait for Demo mask delivery from SEC.
SEC | PROVE | PROVE HR (NRD) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Source mask sending to HQ. | * Additional EUV PSM mask will be sent to HQ.
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error need to be fixed [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March [Auto Repair 3.0 evaluation on LE] * Defect centering test [Auto Repair SimOp evaluation] * Trouble shooting and set-up
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-montioring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : If customer satisfy online demo then move to live evaluation on tool. | * Waiting for Auto Repair 3.0 evaluation completion.
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with new gas chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Pt based Hi-NA mask with Cr buffer is promising. * Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. * Action : HQ progress update to SKH for etch performance. | [EUV PSM (Ru based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) [EUV PSM High-NA (Pt based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH)
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon, Cho) | WLCD 0.5 Software Upgrade Requirement | [S/W upgrade - WLCD 0.5 Release] - Status: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) |  |  | 1. [Application] - Phase offset investigation with AFM underway • Status: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Status: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A |  |  | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM Recovery Attempt | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attach VM with new. : OK (valued for root cause. Possible corruption of network) | Recovery attempt: Scheduled for Thursday
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * will work during bore swap schedule.
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation | * waiting from HQ updates.
SK hynix | AIMS DUV | AIMS fab neo (SoonYoung) | AIMS fab neo Lamp replacement ATP 90degree | * Status: AIMS fab neo ATP * Action: After replacing lamp, SKH requested for ATP result (Lee Hyun Jun) * Result: 0degree results satisfied. 90 degree measurement on Monday.
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: AIMS 1x TTTM * Action: HQ & SK Hynix had discussion for this topic * Result: According to Disar illumination from AIMS 1x #6, its intensity is not uniformity. | Service team have done Trouble shooting on AIMS 1x #6 - Pole Balance : 0.5% - Coma : 0.5% - Issued Defect tool setting Pupil intensity : Uniform SK hynix Process team will confirm tool status.
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible Remaining uncertainties Difference between CDx and CDy currently not explainable Unusual high mask CDU | Further investigations needed - set up meeting with HQ for further discussion at middle of march
SK hynix | AAA | AAA | AAA 2.33 Upgrade Installation Failure | * Status: Need a AAA 2.33 Upgrade (Confirmed SK hynix uses AAA Ver. 2.33 in CW50, 2025) * Task : AAA SW 2.33 upgrade Failure on MAA FAVOR (Test purpose prior to AAA FAVOR inst.) * Action: Installation on MAA FAVOR for Test, it has issue during installation [Solved on MAA FAVOR. caused by license) * Result: SW installation failure with Error message ‘ No storage’ & ‘Need Privilege’ and AAA service Start failure. Log file extracted and delivered to HQ. | * Plan: Completed MAA installation. Will install AAA SW 2.33 to AAA FAVOR (11/04) NEED TO CHECK
SK hynix | AAA | AAA AIMS EUV | SK Hynix VoC Updates | 1. Update the IR file (.rff) to match DUV information and link it with Defect Type 2. Adjust the Defect Number format to four digits. 3. Check if the AAA job name can be modified, including the method and available tokens. 4. Determine if additional settings are needed to fix the issue where measurements are not performed sequentially, even when the TravelingSalesman function is turned off in Batch. | Follow up with "Samsung Case column 27"
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Result: Ein m/o Feb | * Plan: Have measurement result (registration & overlay) from customer |  | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation
SK hynix | PROVE | PROVE neXT | Intro session for PROVE GUI | * Status: A customer has inquired to have desired feature in PROVE. * Action : To have an introduction session for PROVE GUI * Result: | Session will be held in March
SK hynix | PROVE | PROVE neXT | Box/ Stamp Demo | Subject: New clip file request for Demo. Action: Request to Hynix to get a bigger clip file Result: Bigger clip file is delivered to HQ | Process the measurement with new Clip file
SK hynix | PROVE | PROVE neXT | EUV mask requirement for ATP | Subject: Customer need to prepare EUV mask for ATP Action: Request to Sabine regarding spec of EUV mask during ATP Result: Get the draft version of ATP mask requirement | Discuss with customer to specify which pattern will be used for ATP | 3_10
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP completion on 22nd Jan (Signed off 10th March) * Task : Align pending items and ZEISS recipe support with Tekscend * Action: ZEISS has provided recipe what Tekscend requested. |  | 3_10 key
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | VIS alignment error | • Status: VIS alignment fails • Task : To give POA for current VIS alignment fails • Action: the VIS Focus range is so big, that the structure is properly focused. check Find VIS Focus, Use Find Focus, check VIS Config etc. • Result: waiting for customer's response | Load VIS Focus Config and check the selected configuration. Ask for sharing the alignment data Use Find Focus checked? Which TH is chosen? Which VIS Config is loaded? | 3_10

## CW12_old
Cus. | FoB | Tool | Title | Status | Next Plan | Updated | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support | * ( ~ 3/11 ) - FAVOR on site support : Tthe FAVOR for DFI & FAVOR for PROVE in SR1 (Sven Schutze, Tino Kaiser, Katja Notarangelo) | * 03/18 ~ 03/20 : MeRiT EUV PSM discussion (Felix) - SEC & SK Hynix meeting.
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026)
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.2 released on March 20 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW | 3_16 | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.2 released on March 20 | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW | 3_16
SEC | Repair | M50 neXT | Ch8 liquid water upgrade for SiN process | * Status: Samsung requested an upgrade of Ch8 from iced water to liquid water * Task: Special request for Ch8a with 40 µm orifice and Ch8b with 145 µm orifice (Samsung standard) * Action: 1) ZEISS to provide free upgrade to liquid water at the SEC M50 tool 2) SSC application team to support SiN process tuning; Samsung to provide ZEISS with protocol data for tuning | * Priority of liquid water upgrade is low for Samsung. * SSC asked decision to Samsung, go or stop for liquid water upgrade.
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation - 1st alignment meeting is completion on 11st March - Customer Demo schedule has been fixed : 23rd ~ 26th June in Rossdorf. 2) HNA EUV PSM evaluation on LE tool. | * Alignment meeting for HNA EUV PSM has been scheduled on 19th March (Felix will visit Samsung) * 2nd alignment meeting with Samsung for Demo items need to be schedule | 3_16 (Key)
SEC | Repair | Auto Repair (with next) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.2 upgrade(since 20th March) for Auto Repair improvement (for open items close) * Continue Auto Repair evaluation on neXT #1 ~ #4 | 3_16
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : 1) Improvement of selectivity up to 300% with new gas chemistry 2) Ta vs. Cr buffer layer etch performance with new gas chemistry. 3) New Gas candidate need to be informed to Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : ZEISS to initiate discussions to find the root cause | [EUV PSM High-NA (Pt based)] * EUV PMS update meeting has been scheduled on 19th March (Felix will visit Samsung) [EUV PSM Mesh imprint issue on neXT and LE] * Waiting Samsung feedback about HQ questions for issue. | 3_16 (Key)
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : Upgrade to Sentinel v1.6 and DataCenter v1.1 | * Align Tool time with Samsung for upgrade 1.6 / 1.1 of MeRiT Tool Monitoring Sentinel / DataCenter.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: Configured and Powered up the network functionality - System powered up (using two cables) - Samsung completed mandatory security - Windows Server 2022 OS licenses authenticated (all 10 VMs) - Favor team performed resource checks - Samsung Data Center assigned network - Internal clustering done (3 server hosts, 2 switches) - Share storage increased to 10TB - Configured settings to fulfill Samsung security rules - Drilling on FAVOR for DFI completed - ATP batch completed with one failed job | ATP results will be evaluated on March 16th among with the POA for failed job. | 3_16 | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | DFI Upgrade 후에 Log monitoring 후에 event 증가하면 조율 예정 | April
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) |  |  | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | Status: NDA under reviewing by SEC (CW08) * Subject: Phase Metrology & WLCD EUV * Task: precise measurement in Phase Metrology and WLCD | * Estimated review completion mid of March
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Defect numbering mismatch | Status: Defect numbering mismatch Task: to fix Defect numbering mismatch in rff file Action: Investigation required. Figured out root cause file (pos vs RFF) Result: problematic rff files will be shared among with logs | Plan: will receive further data once reoccurred. | 3_16
SEC | AIMS DUV | AIMS 1x (NRD) | AIMS 1x SW Upgrade to Version 6.18.3 | • Status: AIMS 1x 6.18.3 SW need to be upgrade. • Action: NA • Result: No upgrade items found in ftp. | * Plan :All requirement for SW upgrade was submitted through Azure. HQ is going to check and share Target SW version | 3_16
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA SW 2.34 Upgrade Completion | * Status: AAA 2.34 upgrade * Task : AAA SW 2.34 upgrade P4 FAVOR 3.1 * Action: Upgrading AAA SW 2.34 | * Plan: will upgrade AAA SW. Once AIMS EUV DFI upgrade and ATP Done | 3_16
SEC | AAA | AAA FAVOR (P4) (WonTae) (KiWon) | AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | * Plan : HQ recognized root cause, Working on it for future SW | 3_16
SEC | AAA | AAA FAVOR(P4) (WonTae) | FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. Escalated it to HQ | *Plan : Customer shared FAVOR AAA logs and waiting for approval. It will be shared with HQ. | 3_16
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Send some question about FTM and job automation to HQ (Feb 4th) | • Plan: Waiting for HQ feedback for the Gantt chart & answers for the questions + discuss it with HQ online on week of #12 |  | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (Schedule : TBD) • Action: PW has been obtained with blank 2 & 2 blanks were sent to Israel in advance | • Plan: It is delayed due to mask export issue. Once we fix it, restart the process
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: EUVR data was shared by customer. Under analysis at HQ side | • Plan: HQ analyze the data and share the feedback | 3_16
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Need a clear understanding of DAT file rule of checking. * Action: ZEISS delivered the message to customer that ZEISS can not support DAT file which are made by customer program check and recommend to use FTM | * Plan: RegC : waiting FTM S/W roll out. (Aligned ZEISS and Samsung for the new feature required for automation) CDC : Customer will check if there are errors with ForTune DUV with the cases customer raise | 3_16 (Key)
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Postpone resolving the issue for now since full automation is not yet supported. After installing F312 and completing the full automation tests there, we will upgrade F306 to the same version and address this issue if it still persists
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week | * Plan: ZEISS look into the result
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 CSR Document Review | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Have a final version of the document on March 3rd | Completed
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does NOT support 2D jobs (2026-02-23) • Task : Need to use 3D. Due to limitation of SECS GEM 300. Not Support. • Action: Ask to customer to share real measurement result on the simulation files that customer shared last year to compare 2D and 3D result | • Plan : HQ will test SECS GEM at HQ tool to check if 2D job is supported or not + share simulation results compare 3D and 2D | 3_16 (Key)
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung share required files | • Plan: ZEISS perform the demo and discuss the outcome during HQ engineer on site visit(week of March 9th)
SEC | Tuning | ForTune MLM | Shipment schedule | • Situation: ForTune MLM shipment schedule • Task : To check Backup plan with current HQ situation • Action: To check Backup plan with current HQ situation | • Plan: To check Backup plan with current HQ situation including Semi S2 Certification
SEC | PROVE | PROVE neXT (SR1) | LRM feature enablement | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Investigate FAVOR3.0 with HQ engineers * Result: FAVOR3.0 seems fine, but PROVE still couldn't connect to FAVOR3.0 | * Plan: Discuss with HQ regarding PROVE connection
SEC | PROVE | PROVE | In-cell measurement out of spec | Subject: Analyze if correlation mode cause registration offset Action: Correlation quality check is done , which was fine. Result: Request incell accuracy measurement | Waiting for Incell accuracy result from customer
SEC | PROVE | PROVE | TTTM transition to PROVE neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | Monitor the progress of the master tool transition.
SEC | PROVE | PROVE next ( P4 ) | SW upgrade for Automation patch | Subject: SW upgrade required to install automation patch ( 4.15.1 -> 4.16 ) Action: Collect config files from the tool Result: N/A | Install SW package on 3/26 | 3_16
SEC | PROVE | PROVE | High-Performance mode demo | Subject: Customer want to evaluate HPM demo’s resolution Action: Set up the schedule for demo Result: Demo mask will be delivered. (Samsung in preparation) | Demo mask will be delivered around end of March. (HQ tool is ready at the end of April : tool down due to H/W issue) | 3_16 (Key)
SEC | PROVE | PROVE HR (NRD) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Customer visiting has been canceled. | * HQ Source report need to be provided to SKH before 18th May | 3_16 (Key)
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error has been solved [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March [Auto Repair 3.0 evaluation on LE] * Auto Repair evaluation support. [Auto Repair SimOp evaluation] * Trouble shooting and set-up | 3_16
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-monitoring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : If customer satisfy online demo then move to live evaluation on tool. | * Planning for HQ expert visiting for Tool-monitoring live demo. (Target : April ~ July) | 3_16
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with new gas chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Pt based Hi-NA mask with Cr buffer is promising. * Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. * Action : HQ progress update to SKH for etch performance. | [EUV PSM (Ru based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) [EUV PSM High-NA (Pt based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) | 0316 Key (Felix customer on-site meeting on 20th)
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon, Cho) | WLCD 0.5 Software Upgrade Requirement | [S/W upgrade - WLCD 0.5 Release] - Status: Need a S/W upgrade for WLCD 0.5 (scheduled: CW02 in 2026) - WLCD EUV0.5 availability: Week 6 (earliest) | Completed |  | 1. [Application] - Phase offset investigation with AFM underway • Status: AFM data analyzed (6 masks) to understand causes of AIMS EUV phase offset; Mask #6 pending. • Task: Identify structure-induced contributors (e.g., absorber height, edge profile, rounding). • Action: Site #14 selected as baseline; trial AFM scan on Mask 1 planned. • Result: Site-level deviation classified; awaiting HQ feedback. • Plan: Refine correlation model and finalize report by Q3. 2. [Application] Hi-NA In-Die evaluation strategy defined • Status: Mask#3 was misaligned. • Task: • Action: To be informed the demo slot at HQ • Result: • Plan:
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A |  |  | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM Recovery Attempt | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attach VM with new. : OK (valued for root cause. Possible corruption of network) | Recovery attempt: Scheduled for Thursday
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * will work during bore swap schedule.
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation | Short term POA will be applied on next bore swap (Seems GPU in FAVOR not activated) will check | 3_16
SK hynix | AIMS DUV | AIMS fab neo (WonTae, SoonYoung) | AIMS fab neo Lamp replacement ATP 90degree | * Status: AIMS fab neo ATP * Action: After replacing lamp, SKH requested for ATP result (Lee Hyun Jun) * Result: 90 degree measurement on CW12. | * Plan : Lamp replacement will be performed on 3/18 due to intensity low. ATP will be conducted 3/18 - 03/19 | 3_16
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: AIMS 1x TTTM * Action: HQ & SK Hynix had discussion for this topic * Result: Service team had beam alignment. Disar intensity is uniform | *Plan : still CD value difference between #4 & #6. need further discussion with HQ | 3_16
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible Remaining uncertainties Difference between CDx and CDy currently not explainable Unusual high mask CDU | *Further investigations needed - set up meeting with HQ for further discussion at middle of march | priority low
SK hynix | AAA | AAA | AAA 2.34 Upgrade | * Status: Need a AAA 2.34 Upgrade * Task : AAA SW 2.34 upgrade for FAVOR 2.1 & FAVOR 3.1 * Action: SW installation files delivered Done | * Plan: Scheduling SW upgrade for all Servers & SK hynix users in parallel. | 3_16
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Result: Ein m/o Feb | * Plan: Have measurement result (registration & overlay) from customer |  | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation
SK hynix | PROVE | PROVE neXT | Intro session for PROVE GUI | * Status: A customer has inquired to have desired feature in PROVE. * Action : To have an introduction session for PROVE GUI * Result: | Session will be held in March
SK hynix | PROVE | PROVE neXT | Box/ Stamp Demo | Subject: New clip file request for Demo. Action: Request to Hynix to get a bigger clip file Result: Currently, Processing is on hold because PROVE on HQ is down. | Process the measurement with new Clip file (HQ tool is ready at the end of April : tool down due to H/W issue) | 3_16 (Key)
SK hynix | PROVE | PROVE neXT | EUV mask requirement for ATP | Subject: Customer need to prepare EUV mask for ATP Action: Request to Sabine regarding spec of EUV mask during ATP Result: Get the mask layout of ATP mask from HQ | Discuss with customer to specify which pattern will be used for ATP (HQ plan to share design clip for EUV mask) (Hynix plan to fabricate the ATP mask for EUV measurement) | 3_16
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP completion on 22nd Jan (Signed off 10th March) * Task :Pending items discussion * Action: HQ process support is needed, if issue happens on production. | * Waiting for customer feedback for potential process issue on production. | 3_16
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | VIS alignment error | Status: VIS alignment failed (Priority: Low) Task : To give POA for current VIS alignment fails Action: to reproduce current error Result: waiting for tool time | All configuration checked, customer confirmed that only one problematic mask continuously shows vis error. Suspecting mask malformation. | 3_16

## CW12
Cus. | FoB | Tool | Title | Status | Next Plan | Updated | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support | * 03/18 ~ 03/20 : MeRiT EUV PSM discussion (Felix) - SEC & SK Hynix meeting.
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Samsung will decide for using current video signal setting.(Target Completion : March 2026) due to lack of monitoring time.
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung.
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026)
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.2 released on March 20 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW | 3_16 | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.2 released on March 20 | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for upgrade SW | 3_16
SEC | Repair | M50 neXT | Ch8 liquid water upgrade for SiN process | * Status: Samsung requested an upgrade of Ch8 from iced water to liquid water * Task: Special request for Ch8a with 40 µm orifice and Ch8b with 145 µm orifice (Samsung standard) * Action: 1) ZEISS to provide free upgrade to liquid water at the SEC M50 tool 2) SSC application team to support SiN process tuning; Samsung to provide ZEISS with protocol data for tuning | * Priority of liquid water upgrade is low for Samsung. * SSC asked decision to Samsung, go or stop for liquid water upgrade.
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation - 1st alignment meeting is completion on 11st March - Customer Demo schedule has been fixed : 23rd ~ 26th June in Rossdorf. 2) HNA EUV PSM evaluation on LE tool. | * Alignment meeting for HNA EUV PSM has been scheduled on 19th March (Felix will visit Samsung) * 2nd alignment meeting with Samsung for Demo items need to be schedule | 3_16 (Key)
SEC | Repair | Auto Repair (with next) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.2 upgrade(since 20th March) for Auto Repair improvement (for open items close) * Continue Auto Repair evaluation on neXT #1 ~ #4 | 3_16
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 3Q 2027 * Task : Pt based Hi-NA mask with Cr buffer is promising. * Action : 1) Improvement of selectivity up to 300% with new gas chemistry 2) Ta vs. Cr buffer layer etch performance with new gas chemistry. 3) New Gas candidate need to be informed to Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : ZEISS to initiate discussions to find the root cause | [EUV PSM High-NA (Pt based)] * EUV PMS update meeting has been scheduled on 19th March (Felix will visit Samsung) [EUV PSM Mesh imprint issue on neXT and LE] * Waiting Samsung feedback about HQ questions for issue. | 3_16 (Key)
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : Upgrade to Sentinel v1.6 and DataCenter v1.1 | * Align Tool time with Samsung for upgrade 1.6 / 1.1 of MeRiT Tool Monitoring Sentinel / DataCenter.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: Configured and Powered up the network functionality - System powered up (using two cables) - Samsung completed mandatory security - Windows Server 2022 OS licenses authenticated (all 10 VMs) - Favor team performed resource checks - Samsung Data Center assigned network - Internal clustering done (3 server hosts, 2 switches) - Share storage increased to 10TB - Configured settings to fulfill Samsung security rules - Drilling on FAVOR for DFI completed - ATP batch completed with one failed job | ATP results will be evaluated on March 16th among with the POA for failed job. | 3_16 | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | DFI Upgrade 후에 Log monitoring 후에 event 증가하면 조율 예정 | April
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | Service task during DFI upgrade (2026.03.17) |  | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | Status: NDA under reviewing by SEC (CW08) * Subject: Phase Metrology & WLCD EUV * Task: precise measurement in Phase Metrology and WLCD | * Estimated review completion mid of March
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Defect numbering mismatch | Status: Defect numbering mismatch Task: to fix Defect numbering mismatch in rff file Action: Investigation required. Figured out root cause file (pos vs RFF) Result: problematic rff files will be shared among with logs | Plan: will receive further data once reoccurred. | 3_16
SEC | AIMS DUV | AIMS 1x (NRD) | AIMS 1x SW Upgrade to Version 6.18.3 | • Status: AIMS 1x 6.18.3 SW need to be upgrade. • Action: NA • Result: No upgrade items found in ftp. | * Plan :All requirement for SW upgrade was submitted through Azure. HQ is going to check and share Target SW version | 3_16
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA SW 2.34 Upgrade Completion | * Status: AAA 2.34 upgrade * Task : AAA SW 2.34 upgrade P4 FAVOR 3.1 * Action: Upgrading AAA SW 2.34 | * Plan: will upgrade AAA SW. Once AIMS EUV DFI upgrade and ATP Done | 3_16
SEC | AAA | AAA FAVOR (P4) (WonTae) (KiWon) | AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | * Plan : HQ recognized root cause, Working on it for future SW | 3_16
SEC | AAA | AAA FAVOR(P4) (WonTae) | FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. Escalated it to HQ | *Plan : Customer shared FAVOR AAA logs and waiting for approval. It will be shared with HQ. | 3_16
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Send some question about FTM and job automation to HQ (Feb 4th) | • Plan: Waiting for HQ feedback for the Gantt chart & answers for the questions + discuss it with HQ online on week of #12 |  | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (Schedule : TBD) • Action: PW has been obtained with blank 2 & 2 blanks were sent to Israel in advance | • Plan: It is delayed due to mask export issue. Once we fix it, restart the process
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: EUVR data was shared by customer. Under analysis at HQ side | • Plan: HQ analyze the data and share the feedback | 3_16
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Need a clear understanding of DAT file rule of checking. * Action: ZEISS delivered the message to customer that ZEISS can not support DAT file which are made by customer program check and recommend to use FTM | * Plan: RegC : waiting FTM S/W roll out. (Aligned ZEISS and Samsung for the new feature required for automation) CDC : Customer will check if there are errors with ForTune DUV with the cases customer raise | 3_16 (Key)
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Postpone resolving the issue for now since full automation is not yet supported. After installing F312 and completing the full automation tests there, we will upgrade F306 to the same version and address this issue if it still persists
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week | * Plan: ZEISS look into the result
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 CSR Document Review | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Have a final version of the document on March 3rd | Completed
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does NOT support 2D jobs (2026-02-23) • Task : Need to use 3D. Due to limitation of SECS GEM 300. Not Support. • Action: Ask to customer to share real measurement result on the simulation files that customer shared last year to compare 2D and 3D result | • Plan : HQ will test SECS GEM at HQ tool to check if 2D job is supported or not + share simulation results compare 3D and 2D | 3_16 (Key)
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung share required files | • Plan: ZEISS perform the demo and discuss the outcome during HQ engineer on site visit(week of March 9th)
SEC | Tuning | ForTune MLM | Shipment schedule | • Situation: ForTune MLM shipment schedule • Task : To check Backup plan with current HQ situation • Action: To check Backup plan with current HQ situation | • Plan: To check Backup plan with current HQ situation including Semi S2 Certification
SEC | PROVE | PROVE neXT (SR1) | LRM feature enablement | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to fixed to enable LRM feature * Action: Investigate FAVOR3.0 with HQ engineers * Result: FAVOR3.0 seems fine, but PROVE still couldn't connect to FAVOR3.0 | * Plan: Discuss with HQ regarding PROVE connection
SEC | PROVE | PROVE | In-cell measurement out of spec | Subject: Analyze if correlation mode cause registration offset Action: Correlation quality check is done , which was fine. Result: Request incell accuracy measurement | Waiting for Incell accuracy result from customer
SEC | PROVE | PROVE | TTTM transition to PROVE neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | Monitor the progress of the master tool transition.
SEC | PROVE | PROVE next ( P4 ) | SW upgrade for Automation patch | Subject: SW upgrade required to install automation patch ( 4.15.1 -> 4.16 ) Action: Collect config files from the tool Result: N/A | Install SW package on 3/26 | 3_16
SEC | PROVE | PROVE | High-Performance mode demo | Subject: Customer want to evaluate HPM demo’s resolution Action: Set up the schedule for demo Result: Demo mask will be delivered. (Samsung in preparation) | Demo mask will be delivered around end of March. (HQ tool is ready at the end of April : tool down due to H/W issue) | 3_16 (Key)
SEC | PROVE | PROVE HR (NRD) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Customer visiting has been canceled. | * HQ Source report need to be provided to SKH before 18th May | 3_16 (Key)
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error has been solved [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March [Auto Repair 3.0 evaluation on LE] * Auto Repair evaluation support. [Auto Repair SimOp evaluation] * Trouble shooting and set-up | 3_16
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-monitoring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : If customer satisfy online demo then move to live evaluation on tool. | * Planning for HQ expert visiting for Tool-monitoring live demo. (Target : April ~ July) | 3_16
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with new gas chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Pt based Hi-NA mask with Cr buffer is promising. * Task : Open discussion with SKH for Pt based Hi-NA mask etch performance. * Action : HQ progress update to SKH for etch performance. | [EUV PSM (Ru based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) [EUV PSM High-NA (Pt based)] * EUV PSM update meeting has been schedule on 20th March (Felix will visit SKH) | 0316 Key (Felix customer on-site meeting on 20th)
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | Scheduling in May |  | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | Unpowered VM Recovery Attempt | Unpowered VM (xxx.xxx.xxx.59 / 61) - Action: Tried to attach VM with new. : OK (valued for root cause. Possible corruption of network) | Recovery attempt: Scheduled for Thursday (Complted) | to be deleceted
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * will work during bore swap schedule. (co-work with Service, work in next bore swap) 3/16
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation | Short term POA will be applied on next bore swap (Seems GPU in FAVOR not activated) will check | 3_16
SK hynix | AIMS DUV | AIMS fab neo (WonTae, SoonYoung) | AIMS fab neo Lamp replacement ATP 90degree | * Status: AIMS fab neo ATP * Action: After replacing lamp, SKH requested for ATP result (Lee Hyun Jun) * Result: 90 degree measurement on CW12. | * Plan : Lamp replacement will be performed on 3/18 due to intensity low. ATP will be conducted 3/18 - 03/19 | 3_16
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: AIMS 1x TTTM * Action: HQ & SK Hynix had discussion for this topic * Result: Service team had beam alignment. Disar intensity is uniform | *Plan : still CD value difference between #4 & #6. need further discussion with HQ | 3_16
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible Remaining uncertainties Difference between CDx and CDy currently not explainable Unusual high mask CDU | *Further investigations needed - set up meeting with HQ for further discussion at middle of march | priority low
SK hynix | AAA | AAA | AAA 2.34 Upgrade | * Status: Need a AAA 2.34 Upgrade * Task : AAA SW 2.34 upgrade for FAVOR 2.1 & FAVOR 3.1 * Action: SW installation files delivered Done | * Plan: Scheduling SW upgrade for all Servers & SK hynix users in parallel. | 3_16
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Perform the process on the customer mask * Result: Ein m/o Feb | * Plan: Have measurement result (registration & overlay) from customer |  | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation
SK hynix | PROVE | PROVE neXT | Intro session for PROVE GUI | * Status: A customer has inquired to have desired feature in PROVE. * Action : To have an introduction session for PROVE GUI * Result: | Session will be held in March
SK hynix | PROVE | PROVE neXT | Box/ Stamp Demo | Subject: New clip file request for Demo. Action: Request to Hynix to get a bigger clip file Result: Currently, Processing is on hold because PROVE on HQ is down. | Process the measurement with new Clip file (HQ tool is ready at the end of April : tool down due to H/W issue) | 3_16 (Key)
SK hynix | PROVE | PROVE neXT | EUV mask requirement for ATP | Subject: Customer need to prepare EUV mask for ATP Action: Request to Sabine regarding spec of EUV mask during ATP Result: Get the mask layout of ATP mask from HQ | Discuss with customer to specify which pattern will be used for ATP (HQ plan to share design clip for EUV mask) (Hynix plan to fabricate the ATP mask for EUV measurement) | 3_16
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP completion on 22nd Jan (Signed off 10th March) * Task :Pending items discussion * Action: HQ process support is needed, if issue happens on production. | * Waiting for customer feedback for potential process issue on production. | 3_16
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | VIS alignment error | Status: VIS alignment failed (Priority: Low) Task : To give POA for current VIS alignment fails Action: to reproduce current error Result: waiting for tool time | All configuration checked, customer confirmed that only one problematic mask continuously shows vis error. Suspecting mask malformation. | 3_16

## CW13
Cus. | FoB | Tool | Title | Status | Next Plan | Updated | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung (by Samsung H/W team).
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026) (Samsung process team).
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung (by Samsung H/W team).
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026) (Samsung process team).
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.2 released on March 20 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for 5.6.2 version upgrade - Lewis / Target : 30th March for 1 LE or neXT tool. | 3_23 | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.2 released on March 20 | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for 5.6.2 version upgrade - Lewis / Target : 30th March for 1 LE or neXT tool. | 3_23
SEC | Repair | M50 neXT | Ch8 liquid water upgrade for SiN process | * Status: Samsung requested an upgrade of Ch8 from iced water to liquid water (Close) * Task: Special request for Ch8a with 40 µm orifice and Ch8b with 145 µm orifice (Samsung standard) * Action: 1) ZEISS to provide free upgrade to liquid water at the SEC M50 tool 2) SSC application team to support SiN process tuning; Samsung to provide ZEISS with protocol data for tuning | * Samsung has make decision that no Ch8 liquid upgrade for M50. | 3_23
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation - 1st alignment meeting is completion on 11st March - Customer Demo schedule has been fixed : 23rd ~ 26th June in Rossdorf. 2) HNA EUV PSM evaluation on LE tool. | * 2nd alignment meeting with Samsung for Delta Demo items need to be schedule - Dino / Target : Beginning of April. * Customer demo schedule need to be confirmed by HQ - Felix / Target : Beginning of April. | 3_23
SEC | Repair | Auto Repair (with next) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.2 upgrade(since 20th March) for Auto Repair improvement (for open items close) - Lewis / Target : 30th March for 1 LE or neXT tool. * Continue Auto Repair evaluation on neXT #1 ~ #4 - Samsung / Target : TBD | 3_23
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 4Q 2027 for Pt based / CrN blank (Hoya) * Task : Preparing for production with Pt based / CrN Hi-NA mask (Hoya). * Action : 1) Improvement of etch profile & repair performance 2) New gas installation alignment with Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : 1) Test items for fogging damage on M56. 2) Priority of Mesh imprint on LE is lower than M56 fogging damage | [EUV PSM High-NA (Pt based)] * repair profile and performance improvement - Felix / Target : end of April. * Technical analysis for repair. - Samsung / Target :end of July * Prepare for new gas installation on Samsung. - Samsung&SSC / Target :end of April [EUV PSM Mesh imprint issue on neXT and LE] * HQ feedback for fogging damage issue. - Felix / Target : Beginning of April. | 3_23
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : Upgrade to Sentinel v1.7 and DataCenter v1.2 | * Align Tool time with Samsung for upgrade 1.7 / 1.2 of MeRiT Tool Monitoring Sentinel / DataCenter. - TaeHoon / Target : end of April. | 3_23
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: ATP completed 3/20 * Result: All ATP items are in spec, completed at Mar 20th. | Further explanation for Run Rate required (hard aperture vs DFI) in this week. | 3_20 | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | Required to check logs to trace spiral searches | April
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | Service task during DFI upgrade (2026.03.17) | 3_20 | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | Status: NDA under reviewing by SEC (CW08) * Subject: Phase Metrology & WLCD EUV * Task: precise measurement in Phase Metrology and WLCD | * Estimated review completion mid of March
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Defect numbering mismatch | Status: Defect numbering mismatch Task: to fix Defect numbering mismatch in rff file Action: Investigation required. Figured out root cause file (pos vs RFF) Result: problematic rff files will be shared among with logs once re-occurance. | Plan: will receive further data once reoccurred.
SEC | AIMS EUV | AAA EUV (KiWon Cho) | High NA evaluation | * Status: Customer requests High NA evaluation setting * Task : correlating with “High NA strange FoV” issue above * Action: Fix by S/W implementation | Waiting for the FF4 (Full Feature4) release | 3_30
SEC | AIMS EUV | AIMS EUV 3.0 (Kiwon Cho) | High NA strange FoV | * Status: 90 deg Mask alignment setting is a possible cause * Task : root cause analysis done * Acrion: S/W implementation (Found the root-cause To be rolled out, FF4 expected) | Waiting for the FF4 release | 3_30
SEC | AIMS DUV | AIMS 1x (NRD) | AIMS 1x SW Upgrade to Version 6.18.3 | • Status: AIMS 1x 6.18.3 SW need to be upgrade. Cause 6.15 have an issue with init too long. • Action: S/W upgraded 6.12 to 6.15. found init took so long. • Result: Need another version upgrade. | * Plan: Upgrade Tool S/W Ver 6.18.3 (Current: 6.12). Target: end of March | 3_23
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | AAA SW Upgrade | * Status: AAA 2.34 upgrade (Current: 2.33) (Target :2.34) * Task : AAA SW 2.34 upgrade * Action: Shared installer AAA SW 2.34 in CW11 | * Plan: AAA 2.34 SW upgrade in CW14 | 3_23
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | P2 FAVOR 3.1 connection | * Status: Switching the FAVOR Server connections (From NRD to P2 Data-Center: FAVOR 3.1) * Task : Change AAA Server for Tools (2 x AIMS-1x, AIMS FabNeo, AIMS EUV 1.0) * Action: 1) Need to update Configuration in FAVOR and Tools 2) HQ will prepare SOP | * Plan: Connection switch task will be implemented at P2 in CW14 | 3_23
SEC | AAA | AAA FAVOR (P4) (WonTae) (KiWon) | AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | * Plan : Awaiting until AIMS EUV roll out the New S/W with feature (Root Cause: AIMS EUV S/W) | 3_23
SEC | AAA | AAA FAVOR(P4) (WonTae) | FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Abnormal event from AimsAutoAnalysisServerlog on Feb 10th. | *Plan : Waiting for Data transfer from customer. (Estimated timeline : CW 13) | 3_23
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | • Situation: SECS GEM 300 Application part • Task : Job creation automation preparation • Action: Discuss FTM workflow with HQ and customer (March 18th) | • Plan: HQ Check if customer requirement for FTM is applicable (Target date : e/o May) Requirement: To use Normalized R drop Option for mesh size 50, 100 and 200um Etc. | 3_23 | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | • Situation: Full fields demo – Feb with demo tool • Task : Full fields demo with demo tool on Feb (Schedule : TBD) • Action: Export license approval is completed | • Plan: Ship the mask to HQ once the export is available (Target date : Once airspace has been opened due to geopolitical issue) | 3_23
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | • Situation: Full fields demos (2 demos) – Mar with HVM tool • Task : Two Full fields demo on Mar with alpha or beta tool • Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | • Situation: Blank 5 mask process (Redo EUV CDC after RegC) • Task : HQ perform the process RegC and EUV CDC both at HQ side • Action: EUVR data was shared by customer. Under analysis at HQ side | • Plan: HQ analyze the data and share the feedback (estimated getting feedback from HQ, is end of March) | 3_16
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | • Situation: Customer visit to HQ for technical discussion and tool review • Task : Align the schedule and agenda of customer visit • Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD) (Priority: Low)
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta) (Rought timeline: After May)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (RegC and CDC both) - (Priority: Low) * Task : Need a clear understanding of DAT file rule of checking. * Action: ZEISS delivered the message to customer that ZEISS can not support DAT file which are made by customer program check and recommend to use FTM | * Plan: RegC : waiting FTM S/W roll out. (Aligned ZEISS and Samsung for the new feature required for automation) CDC : Customer will check if there are errors with ForTune DUV with the cases customer raise | 3_16 (Key)
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Postpone resolving the issue for now since full automation is not yet supported. After installing F312 and completing the full automation tests there, we will upgrade F306 to the same version and address this issue if it still persists
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week * Result: Need a further action. | * Plan: ZEISS look into the result
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 CSR Document Review | • Situation: ForTune DUV #2 (F312) CSR discussion (2026-02-23) • Task : Have final version of Fortune DUV #2 (F312) CSR document by e/o Feb • Action: Have a final version of the document on March 3rd | Completed | to be deleted
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | • Situation: ForTune DUV #2 (F312) SECS GEM 300 does NOT support 2D jobs (2026-02-23) • Task : Need to use 3D. Due to limitation of SECS GEM 300. Not Support. • Action: Ask to customer to share real measurement result on the simulation files that customer shared last year to compare 2D and 3D result * Result: will support 3D. | • Plan : HQ will test SECS GEM at HQ tool to check if 2D job is supported or not + share simulation results compare 3D and 2D by this week | 3_16 (Key)
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | • Situation: High resolution RegC demo (2026-02-23) • Task : Perform high resolution RegC demo and share relevant files (job files and induced files) • Action: Samsung shared required files | • Plan : Share simulation results from HQ (Target date : e/o March) | 3_23
SEC | Tuning | ForTune MLM | Shipment schedule | • Situation: ForTune MLM shipment schedule • Task : To check Backup plan with current HQ situation • Action: To check Backup plan with current HQ situation | • Plan: To check Backup plan with current HQ situation including Semi S2 Certification
SEC | PROVE | PROVE | In-cell measurement out of spec (Priority: High) | Subject: Analyze if correlation mode cause registration offset Action: Correlation quality check is done , which was fine. Result: Request incell accuracy measurement | Waiting for Incell accuracy result from customer (waiting since Feb) * Link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=778865" | high
SEC | PROVE | PROVE | TTTM transition to PROVE neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | Monitor the progress of the master tool transition.
SEC | PROVE | PROVE | High-Performance mode demo | Subject: Customer want to evaluate HPM demo’s resolution Action: Set up the schedule for demo Result: Demo mask will be delivered. (Samsung in preparation) | Demo mask will be delivered around end of March. (HQ tool is ready at the end of April : tool down due to H/W issue)
SEC | PROVE | PROVE HR (NRD) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Task: Follow up with HQ and manage the issue with higher priority * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | * Plan: Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SK hynix | PROVE | PROVE neXT | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation (Estimated b/o May due to tool issue in HQ)
SK hynix | PROVE | PROVE neXT | Intro session for PROVE GUI | * Status: A customer has inquired to have desired feature in PROVE. * Action : To have an introduction session for PROVE GUI * Result: Customer requested several feature request to integrates PROVE SW into their automated workflow. | The customer's request will be reflected in the SW release by HQ Software team ( Target : 2026 Dec ) | 3_23
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Customer visiting has been canceled. | * HQ Source report need to be provided to SKH before 18th May
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error has been solved [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March - SangIk & DongHwi / Target : end of March [Auto Repair 3.0 evaluation on LE] * Auto Repair evaluation support. - SangIk & DongHwi / Target : end of 2026 [Auto Repair SimOp evaluation] * Trouble shooting and set-up - SangIk & DongHwi / Target : end of June
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-monitoring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : If customer satisfy online demo then move to live evaluation on tool. | * Planning for HQ expert visiting for Tool-monitoring live demo. - David & TaeHoon / Target : April ~ July
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with Cl based chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Abs. materials is fixed as RuPt, SKH will decide materials for buffer layer. Target : 2028 for Mask / 2029 for wafer. * Task : Open discussion with SKH for buffer layer candidate - Candidate : CrN / no buffer * Action : HQ will provide additional data what customer request. | [EUV PSM (Ru based)] * HQ will provide status update - Felix / Target : TBD [EUV PSM High-NA (Pt based)] * Cap layer selectivity test with exist and new chemistry - Felix & SKH / Target : TBD. | 3_23
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | [SSD Storage Expansion] * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea - Cross-charge approval: Confirmed by Menno * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | Scheduling in May |  | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | AIMS EUV 3.0 (SoonYoung Lee) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * H/W action need to be done (Stage Jump), estimated in April. - Ticket transferred to Service from Apps.
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation | * will figure out, ticket is going to open in this week. (Seems GPU in FAVOR not activated) will check
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Threshold/CD fluctuation | Status : AAA Analysis Task : Evaluate of RST jump is required on-site | • Plan : HQ service prepares PoA to check. Then local team will follow up onsite.
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Slow DFI algorithm issue | Status : Algorithm re-deployment paused Task : prepare new configuration file (.xml) | • Plan : To prepare algorithm deployment during next bore swap.
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Separation of license Dongle | SK requests to additional dongle to separate AE office apps and AAA | Once a dongle prepares, proceed the separation.
SK hynix | AIMS DUV | AIMS fab neo (WonTae) | Low intensity with New Lamp (Hamamatsu) | * Status: Hamamatsu lamp has low intensity. Customer request Lamp replacement & ATP * Action: Replaced the lamp and Done ATP measurement in March * Result: Due to intensity low, New lamp replacement is needed on April. | * Plan : Next Lamp replacement date : 4.30 - 4.31 | 3_23
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: Defined the Gap between SK hynix and ZEISS with AIMS 1x TTTM Specification. * Action: HQ & SK Hynix had discussion for this topic in CW10 * Result: H/W action involved. (Beam alignment. Disar intensity is uniform) in b/o March | * Plan : Will have a customer meeting with HQ on CW 14 - Discussion with Specification gap | 3_23
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: After 2nd cleaning step a significant CD change is visible Remaining uncertainties Difference between CDx and CDy currently not explainable Unusual high mask CDU | * Further investigations needed. - set up meeting with HQ for further discussion after Matthias maternity leave (~4/11) | 3_23
SK hynix | AAA | AAA | AAA SW Upgrade | * Status: AAA SW Upgrade Done in CW12 * Action: Upgrade done Ver 2.34 on Server and Client for FAVOR 2.1 & 3.1 (CW 13, 3/17) * Result: Completed | - N/A | to be deleted
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Post registration and overlay data was shared | * Plan: HQ analyze the data if overlay has been improved (Target date : e/o April) | 3_23 | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT | Box/ Stamp Demo | Subject: New clip file request for Demo. Action: Request to Hynix to get a bigger clip file Result: Currently, Processing is on hold because PROVE on HQ is down. | Process the measurement with new Clip file (HQ tool is ready at the end of April : tool down due to H/W issue)
SK hynix | PROVE | PROVE neXT | EUV mask requirement for ATP | Subject: Customer need to prepare EUV mask for ATP Action: Request to Sabine regarding spec of EUV mask during ATP Result: Customer will send out their EUV PM mask to test at HQ. | The local team will ship Customer mask to HQ ( Target : 2026 May ) | 3_23
SEC | PROVE | PROVE next ( P4 ) | SW upgrade for Automation patch | Subject: SW upgrade required to install automation patch ( 4.15.1 -> 4.16 ) Action: Collect config files from the tool Result: N/A | Install SW package on 3/26
SEC | PROVE | PROVE neXT (SR1) | LRM feature enablement (FAVOR) (Priority: High) | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to be fixed to enable LRM feature * Action: Investigate FAVOR3.0 with HQ engineers (2026-Mar-06) * Result: FAVOR3.0 seems fine, but PROVE still couldn't connect to FAVOR3.0. Need a PROVE FoB Help | * Plan: Discuss with HQ regarding PROVE connection Help Need: From PROVE FoB with 785216 * link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=785216"
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP completion on 22nd Jan (Signed off 10th March) * Task :Pending items discussion * Action: HQ process support is needed, if issue happens on production. | * Waiting for customer feedback for potential process issue on production. | 3_16
Tekscend | AIMS DUV | AIMS Fab Neo (SoonYoung) | VIS alignment error | Status: VIS alignment failed (Priority: Low) Task : To give POA for current VIS alignment fails Action: to reproduce current error Result: MA completed with manual align (Completed) | - N/A | to be deleted

## CW14
Cus. | FoB | Tool | Title | Status | Next Plan | Updated | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung (by Samsung H/W team).
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026) (Samsung process team).
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung (by Samsung H/W team).
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: Mar 2026) (Samsung process team).
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.2 released on March 20 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for 5.6.2 version upgrade - Lewis / Target : SEC/GEM bug is observed at 4.15.2 version. Therefore. 5.6.2 version upgrade is postponed until find rootcase. | 3_31 | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.2 released on March 20 | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * SSC will align tool time with Samsung for 5.6.2 version upgrade - Lewis / Target : SEC/GEM bug is observed at 4.15.2 version. Therefore. 5.6.2 version upgrade is postponed until find rootcase. | 3_31
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation - 1st alignment meeting is completion on 11st March - Customer Demo schedule has been fixed : 23rd ~ 26th June in Rossdorf. 2) HNA EUV PSM evaluation on LE tool. | * 2nd alignment meeting with Samsung for Delta Demo items need to be schedule - Dino / Target : Beginning of April. * Customer demo schedule need to be confirmed by HQ - Felix / Target : Beginning of April. | 3_23
SEC | Repair | Auto Repair (MeRiT neXT) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.2 upgrade(since 20th March) for Auto Repair improvement (for open items close) - Lewis / Target : SEC/GEM bug is observed at 4.15.2 version. Therefore. Upgrade schedule is postponed until find rootcase. * Continue Auto Repair evaluation on neXT #1 ~ #4 - Samsung / Target : TBD | 3_31
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 4Q 2027 for Pt based / CrN blank (Hoya) * Task : Preparing for production with Pt based / CrN Hi-NA mask (Hoya). * Action : 1) Improvement of etch profile & repair performance 2) New gas installation alignment with Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : 1) Test items for fogging damage on M56. 2) Priority of Mesh imprint on LE is lower than M56 fogging damage | [EUV PSM High-NA (Pt based)] * repair profile and performance improvement - Felix / Target : end of April. * Technical analysis for repair. - Samsung / Target :end of July * Prepare for new gas installation on Samsung. - Samsung & SSC / Target :end of April [EUV PSM Mesh imprint issue on neXT and LE] * HQ feedback for fogging damage issue. - Felix / Target : Beginning of April. | 3_23
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : 1) Upgrade to Sentinel v1.7 and DataCenter v1.2 2) Technical meeting with customer (by HQ expert) | * Align Tool time with Samsung for upgrade 1.7 / 1.2 of MeRiT Tool Monitoring Sentinel / DataCenter. - TaeHoon / Target : end of April. * HQ On-site technical meeting with customer - David / Target : week of May 11. | 3_30
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) | ZEISS CAA Mask alignment redefine | Targeted on next bore swap (CW15) * Status: CAA mask align redefine * Task: to make MA coordinate same as P4 AE3's MA coordinates * Action: to be executed in next week * Result: N/A | * Mask Re-definition in next bore swap timeline in CW15 | 3_30
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: ATP completed 3/20 * Result: All ATP items are in spec, completed at Mar 20th. | Further explanation for Run Rate required (hard aperture vs DFI) in this week. | 3_20 | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | Required to check logs to trace spiral searches | April
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | Service task during DFI upgrade (2026.03.17) | 3_20 | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | * Status: Getting NDA for Phase Metrology & WLCD EUV * Task: precise measurement using Aerial Image * Action: SEC expect to have AIMS EUV raw data available - SEC have ability to have resist modeling | * Plan: 1. Setup call with SEC and HQ after easter holiday (Dr. Roh)
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Defect numbering mismatch | * Status: Defect numbering mismatch * Task: to fix Defect numbering mismatch in rff file * Action: Investigation required. Figured out root cause file (pos vs RFF) * Result: problematic rff files will be shared among with logs once re-occurrence. | * Plan: will receive further data once reoccurred. | 3_30
SEC | AIMS EUV | AAA EUV 3.0 (KiWon Cho) | High NA evaluation | * Status: Customer requests High NA evaluation setting * Task: correlating with “High NA strange FoV” issue above |  | 3_30
SEC | AIMS EUV | AIMS EUV 3.0 (KiWon Cho) | High NA strange FoV | * Status: 90 deg Mask alignment setting is a possible cause * Task: root cause analysis done * Action: Found the root-cause To be rolled out (FF4 expected) | Waiting for the FF4 release | 3_30
SEC | AIMS DUV | AIMS 1x (NRD) (WonTae) | AIMS 1x SW Upgrade to Version 6.18.3 | * Status: AIMS 1x 6.18.3 SW need to be upgrade. Cause 6.15 have an issue with init too long. * Action: S/W upgraded 6.12 to 6.15. found init took so long. * Result: HQ have shared new Database file. Ready to upgrade | * Plan: Upgrade Tool S/W Ver 6.18.3 (Current: 6.12). Target: CW16 | 3_30
SEC | AAA | AAA (FAVOR P4) (Kim, WonTae) | AAA SW Upgrade | * Status: AAA 2.34 upgrade (Current: 2.33) (Target :2.34) * Task : AAA SW 2.34 upgrade * Action: Customer have installed AAA 2.34.1 to DUV VM & EUV VM of FAVOR 3.1 in DataCenter | * Plan: 2.34 will be applied to FAVOR 3.0 (P4) & Samsung Engineer & Operator PC on 4/2. | 3_30
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | P2 FAVOR 3.1 connection | * Status: Switching the FAVOR Server connections (From NRD to P2 Data-Center: FAVOR 3.1) * Task : Change AAA Server for Tools (2 x AIMS-1x, AIMS FabNeo, AIMS EUV 1.0) * Action: 1) Need to update Configuration in FAVOR and Tools 2) HQ will prepare SOP | * Plan: Connection switch task will be implemented at P2 in 4/2 | 3_30
SEC | AAA | AAA FAVOR (P4) (WonTae) | AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | * Plan : Awaiting until AIMS EUV roll out the New S/W with feature (Root Cause: AIMS EUV S/W) | 3_23
SEC | AAA | AAA FAVOR(P4) (WonTae) | FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Customer shared Log files from AAA. The log files were uploaded FTP | *Plan : HQ will investigate the log files and release New SW that fixed the bugs | 3_30
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | * Situation: SECS GEM 300 Application part * Task : Job creation automation preparation * Action: Discuss FTM workflow with HQ and customer (March 18th) | • Plan: HQ Check if customer requirement for FTM is applicable (Target date : e/o May) Requirement: To use Normalized R drop Option for mesh size 50, 100 and 200um Etc. | 3_23 | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | * Situation: Full fields demo – Feb with demo tool * Task : Full fields demo with demo tool on Feb (Schedule : TBD) * Action: Export license approval is completed | • Plan: Ship the mask to HQ once the export is available (Target date : Once airspace has been opened due to geopolitical issue) | 3_23
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | * Situation: Full fields demos (2 demos) – Mar with HVM tool * Task : Two Full fields demo on Mar with alpha or beta tool * Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | * Situation: Blank 5 mask process (Redo EUV CDC after RegC) * Task : HQ perform the process RegC and EUV CDC both at HQ side * Action: EUVR data was shared by customer. Under analysis at HQ side | • Plan: HQ analyze the data and share the feedback (estimated getting feedback from HQ, is end of March) | 3_16
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | * Situation: Customer visit to HQ for technical discussion and tool review * Task : Align the schedule and agenda of customer visit * Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD) (Priority: Low)
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta) (Rought timeline: After May)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (CDC) - (Priority: Low) * Task : Share automation information in case .dat file cause errors. * Action: ZEISS and Samsung checked together that the cases Samsung concern with wrong .dat file bring error message before start job process. | * Plan: To share automation information in case .dat file cause error message - S16F12 ACKA - Which ALID will be updated the host ? - Which step will be shown the error? (P-job creation or fail?) (Target date : m/o April) | 3_30
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Postpone resolving the issue for now since full automation is not yet supported. After installing F312 and completing the full automation tests there, we will upgrade F306 to the same version and address this issue if it still persists
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week * Result: Need a further action. | * Plan: ZEISS look into the result
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | * Situation: ForTune DUV #2 (F312) SECS GEM 300 support 2D jobs * Task : Need to test 2D jobs with the tool * Action: Ask to customer to share real measurement result on the simulation files that customer shared last year to compare 2D and 3D result | • Plan : HQ will test SECS GEM at HQ tool to check if 2D job is supported or not + ZEISS compare 3D and 2D results to convince customer to use 3D jobs even 2D job works (Target date : m/o April) | 3_30
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | * Situation: High resolution RegC demo (2026-02-23) * Task : Perform high resolution RegC demo and share relevant files (job files and induced files) * Action: Samsung shared required files | • Plan : Share simulation results from HQ (Target date : e/o March) | 3_23
SEC | PROVE | PROVE neXT (SR1) | LRM feature enablement (FAVOR) (Priority: High) | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to be fixed to enable LRM feature * Action: Investigate FAVOR3.0 with HQ engineers (2026-Mar-06) * Result: FAVOR3.0 seems fine, but PROVE still couldn't connect to FAVOR3.0. Need a PROVE FoB Help | * Plan: Discuss with HQ regarding PROVE connection Help Need: From PROVE FoB with 785216 * link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=785216" | (Priority: High)
SEC | PROVE | PROVE | In-cell measurement out of spec (Priority: High) | * Status: Analyze if correlation mode cause registration offset * Action: Correlation quality check is done , which was fine. HQ commented the feedback that they need Incell accuracy data ASAP * Result: Request incell accuracy measurement | Waiting for Incell accuracy result from customer ( waiting since Feb ) / ( Target : within April ) * Link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=778865" | (Priority: High) | * Link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=778865"
SEC | PROVE | PROVE | TTTM transition from HR to neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | Monitor the progress of the master tool transition.
SEC | PROVE | PROVE next ( P4 ) | SW upgrade for Automation patch | * Subject: SW upgrade required to install automation patch ( 4.15.1 -> 4.16 ) * Action: Collect config files from the tool * Result: SW upgraded successfully. Need to check CSV file storing. (particle monitoring job) | Install SW package on 3/26 ( Completed ) | 3_30
SEC | PROVE | PROVE | High-Performance mode demo | * Status: Customer want to evaluate HPM demo’s resolution * Action: 1) Set up the schedule for demo 2) Align tool time for demo measurement * Result: Demo mask will be delivered. ( Samsung in preparation ) | Demo mask will be delivered from customer on April 3rd ( Expected ) Tool time for demo measurement on HQ would be around end of May | 3_30
SEC | PROVE | PROVE HR (NRD) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | Request HQ to escalate the priority and provide a concrete action plan as soon as possible.
SEC | PROVE | PROVE | SW feature request - Offline re-measurement | * Status: Customer requested new SW feature * Action: Created SW feature request ticket to escalate to HQ * Result: - | Waiting for HQ feedback ( Target : 2026 May ) | 3_30
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Customer visiting has been canceled. | * HQ Source report need to be provided to SKH before 18th May
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error has been solved [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March (SangIk & DongHwi / Target : end of March) [Auto Repair 3.0 evaluation on LE] * Auto Repair evaluation support. (SangIk & DongHwi / Target : end of 2026) [Auto Repair SimOp evaluation] * Trouble shooting and set-up (SangIk & DongHwi / Target : end of June)
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-monitoring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : (1) If customer satisfy online demo then move to live evaluation on tool. (2) HQ on-site Demo in SKH. | * Planning for HQ expert visiting for Tool-monitoring live demo. (David & TaeHoon / Target : Week of May 11) | 3_30
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with Cl based chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Abs. materials is fixed as RuPt, SKH will decide materials for buffer layer. Target : 2028 for Mask / 2029 for wafer. * Task : Open discussion with SKH for buffer layer candidate - Candidate : CrN / no buffer * Action : HQ will provide additional data what customer request. | [EUV PSM (Ru based)] * HQ will provide status update - Felix / Target : TBD [EUV PSM High-NA (Pt based)] * Cap layer selectivity test with exist and new chemistry - Felix & SKH / Target : TBD. | 3_23
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea (Cross-charge approval: Confirmed by Menno) * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | Scheduling in May | May | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * H/W action need to be done (Stage Jump), estimated in April. - Ticket transferred to Service from Apps.
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Threshold/CD fluctuation | Status : AAA Analysis Task : Evaluate of RST jump is required on-site (RST: Retile Stage) | • Plan : verify tool performance once done H/W action below. HQ service prepares PoA to check. Then local team will follow up onsite. | 3_30
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | AE3 DFI Measurement Escalation | * Status: excessive time taken for AE3 DFI measure * Task : Escalate DFI measurement result and CSI to HQ * Action: CSI gathered, ticket creation required for escalation * Result: Over 15m/s taken for one site. *nightly*.xml exported for escalation | * will figure out, ticket is going to open in this week. (Seems GPU in FAVOR not activated) will check in upcoming bore swap | 3_30
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Slow DFI algorithm issue | * Status : Found the issue at inactive GPU * Task : Restart #2/ #3 Server during next bore swap. * FYI : Fan-noise happened at server #1 | Restart FAVOR servers during next bore swap. | 3_30
SK hynix | AAA EUV AIMS EUV | AAA EUV AIMS EUV 3.0 (WonTae) (KiWon) | Separation of license Dongle | * Status: Separation License dongle in SW AAA client & EUV batch Editor * Action: Escalated it to HQ. Requested Physical Dongle to separate them * Result: need discussion with HQ | Plan : Once a dongle prepares, proceed the separation. | 3_30
SK hynix | AIMS DUV | AIMS fab neo (WonTae) | Low intensity with New Lamp (Hamamatsu) | * Status: Hamamatsu lamp has low intensity. Customer request Lamp replacement & ATP * Action: Replaced the lamp and Done ATP measurement in March * Result: Due to intensity low, New lamp replacement is needed on April. | * Plan : Next Lamp replacement date : 4.30 - 4.31 | 3_23
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: Defined the Gap between SK hynix and ZEISS with AIMS 1x TTTM Specification. * Action: HQ & SK Hynix had discussion for this topic in CW10 * Result: H/W action involved. (Beam alignment. Disar intensity is uniform) in b/o March | * Plan : Will have a customer meeting with HQ on CW 16 - Discussion with Specification gap | 3_23
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: DUV WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: No internal draft until 23rd of April | * Plan : HQ will share DUV WLCD strategy after Germany Easter Holiday | 3_30
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Post registration and overlay data was shared | * Plan: HQ analyze the data if overlay has been improved (Target date : e/o April) | 3_23 | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT (KiWon) | Measurement feasibility demo | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | After receiving the demo results from HQ, deliver the result to the customer for further evaluation (Estimated b/o May due to tool issue in HQ)
SK hynix | PROVE | PROVE neXT (DongHoon) | SW requirement for Production | * Status: A customer has inquired to have desired feature in PROVE. * Action : Customer requested several feature request to integrates PROVE SW into their automated workflow. * Result: Created multiple ticket to escalate to HQ regarding SW feature that customer requested. | The customer's request will be reflected in the SW release by HQ Software team ( Target : 2026 Dec ) | 3_23
SK hynix | PROVE | PROVE neXT (KiWon) | Box/ Stamp Demo | * Subject: New clip file request for Demo. * Action: Request to Hynix to get a bigger clip file * Result: Currently, Processing is on hold because PROVE on HQ is down. | Process the measurement with new Clip file (HQ tool is ready at the end of April : tool down due to H/W issue)
SK hynix | PROVE | PROVE neXT (KiWon) | EUV mask requirement for ATP | * Status : Need HQ help for further support for EUV mask fabrifaction for ATP. * Task : three question below. * Action: 1) Need to be removed the L0 layer, which is currently applied as an overall layer. 2) Justification is required explaining for reverse tonality to the pattern. 3) Need a confirmation for the clear field indication, is reverse tonality required. | * Awaiting HQ feedback. * Plan to ship customer mask to HQ ( Target : 2026 May ) | Priority
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP completion on 22nd Jan (Signed off 10th March) * Task :Pending items discussion * Action: HQ process support is needed, if issue happens on production. | * Waiting for customer feedback for potential process issue on production. | 3_16
Note on F3: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: @Lee, SangIk 해당 내용 일정은 언제쯤 정도일까요? 삼성 feedback 취합
Note on F8: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: @Lee, SangIk Target 3/30 업데이트 부탁드립니다.
Note on F14: [스레드 댓글] 사용 중인 버전의 Excel에서 이 스레드 댓글을 읽을 수 있지만 파일을 이후 버전의 Excel에서 열면 편집 내용이 모두 제거됩니다. 자세한 정보: https://go.microsoft.com/fwlink/?linkid=870924. 댓글: @Lee, SoonYoung 해당 내용 업데이트 없나요? 아직 진행되지 않았다면 일정 업데이트 해주세요

## CW15
Cus. | FoB | Tool | Title | Status | Next Plan | Updated | Reference (Internal If anything)
HQ | All | HQ visit | HQ on site support | *Repair Apps engineer exchange - Engineer : Donghwi Kim - Period : 8th April ~ 8th May - Place : Rossdorf in Germany.
SEC | Repair | LE#1 (m 85) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN process setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung (by Samsung H/W team).
SEC | Repair | LE#1 (m 85) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization * Action : Reverted to Samsung Video signal due to high Gap. | * Decision on current video signal usage pending due to limited monitoring time (Target: April 2026) (Samsung process team).
SEC | Repair | LE#2 (m 93) | Application ATP | Final ATP Sign-off: Signed on 29th July 2025. * Status: SiN setup delay * Task: Compensation discussion * Action: Gas sensor parts proposed | * waiting for feedback from Samsung (by Samsung H/W team).
SEC | Repair | LE#2 (m 93) | ATP pending items | [EUV etch ESB signal issue] * Status: Min ESB signal fluctuation without impact the tool operation. * Task: Signal stabilization. * Action : Samsung video signal restored. | * Decision on current video signal usage pending due to limited monitoring time (Target: April 2026) (Samsung process team).
SEC | Repair | LE#3 (m106) in P4 | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] by Lewis * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SEC/GEM300 bug fix * Action: SW 5.6.2 released on March 20 [RS4 contamination test] * Status: RS4 contamination using RS4 gas is required * Task: Obtain Samsung approval to open the RS4 bottle * Action : Waiting for Samsung’s permission [Reduce backside particle (H/W)] * Status: Backside particles observed on the mask * Task: Cleaning of the mask handling system * Action : HW action required | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * Completed S/W upgrade Ver 4.15.2 on M71 (neXT in NRD) * Need a monitoring time until 12nd April * Next plan: S/W upgrade (5.6.2) for LE on 13rd April on M93 (LE#2 in NRD) | 04_06 | * Completed ZAN1: 16th Oct. 2025
SEC | Repair | LE#4 (m110 P4) Lewis | ATP pending items | [SW 5.6.0 upgrade for SEC/GEM 300 bug fix] * Status: SW 5.6.0 upgrade required to fix SEC/GEM300 bug * Task: Perform SW upgrade and verify SECS/GEM300 bug fix * Action: SW 5.6.2 released on March 20 | [SW 5.6.2 upgrade for SEC/GEM 300 bug fix] * Completed S/W upgrade Ver 4.15.2 on M71 (neXT in NRD) * Need a monitoring time until 12nd April * Next plan: S/W upgrade (5.6.2) for LE on 13rd April on M93 (LE#2 in NRD) | 04_06
SEC | Repair | MeRiT AE | MeRiT AE demo | * Status: Samsung plans to visit HQ for AE demo in June 2026 * Task: Align demo items with Samsung * Action: Demo items 1) Delta column performance evaluation - 1st alignment meeting is completion on 11st March - Customer Demo schedule has been fixed : 23rd ~ 26th June in Rossdorf. 2) HNA EUV PSM evaluation on LE tool. | * 2nd alignment meeting with Samsung for Delta Demo items need to be schedule - Dino / Target : Beginning of April. * Customer demo schedule need to be confirmed by HQ - Felix / Target : Beginning of April. | 3_23
SEC | Repair | Auto Repair (MeRiT neXT) | Auto Repair 3.0 | * Status: AR evaluation in progress and open items under improvement * Task: Collect Auto Repair 3.0 success rate data (40%) * Action: 1) Suggestion sign-off with customer 2) Discussion to close open items | * SW 4.15.2 upgrade(since 20th March) for Auto Repair improvement (for open items close) * Completed S/W upgrade Ver 4.15.2 on M71 (neXT in NRD) * Auto Repair eval. Ongoing neXT #1 ~ #4 - Samsung / Target : TBD | 04_06
SEC | Repair | EUV PSM Process | EUV PSM Collaboration items | [EUV PSM High-NA (Pt based)] * Status : Samsung has plan to start production from 4Q 2027 for Pt based / CrN blank (Hoya) * Task : Preparing for production with Pt based / CrN Hi-NA mask (Hoya). * Action : 1) Improvement of etch profile & repair performance 2) New gas installation alignment with Samsung to prepare Samsung EHS. [EUV PSM Mesh imprint issue on neXT and LE] * Status : Mesh imprint observed after EUV PSM etch process * Task : Joint collaboration between Samsung and ZEISS to identify root cause * Action : 1) Test items for fogging damage on M56. 2) Priority of Mesh imprint on LE is lower than M56 fogging damage | [EUV PSM High-NA (Pt based)] * repair profile and performance improvement - Felix / Target : end of April. * Technical analysis for repair. - Samsung / Target :end of July * Prepare for new gas installation on Samsung. - Samsung & SSC / Target :end of April [EUV PSM Mesh imprint issue on neXT and LE] * HQ feedback for fogging damage issue. - Felix / Target end of April. | 3_23
SEC | Repair | Tool Monitoring (with LE) | Tool-monitoring improvement (Sentinel & Datacenter) | * Status : Tool monitoring improvement is ongoing * Task : Sentinel and DataCenter SW upgrades according to the roadmap * Action : 1) Upgrade to Sentinel v1.7 and DataCenter v1.2 2) Technical meeting with customer (by HQ expert) | * Align Tool time with Samsung for upgrade 1.7 / 1.2 of MeRiT Tool Monitoring Sentinel / DataCenter. - TaeHoon / Target : end of April. * HQ On-site technical meeting with customer - David / Target : week of May 11. | 3_30
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) | ZEISS CAA Mask alignment redefine | Targeted on next bore swap (CW15) * Status: CAA mask align redefine * Task: to make MA coordinate same as P4 AE3's MA coordinates * Action: to be executed in next week * Result: N/A | * Mask Re-definition in next bore swap timeline in CW15 | 3_30
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | DFI Upgrade Communication Setup | [DFI Upgrade] Targeting completion b/o March 2026 * Status: Powered up FAVOR 3.1 at P2 data center and Configured IP * Task: Make Network FAVOR 3.1 (P2) and Tool (NRD). * Action: ATP completed 3/20 * Result: All ATP items are in spec, completed at Mar 20th. | Further explanation for Run Rate required (hard aperture vs DFI) in this week. | 3_20 | • Status: Samsung ready to close SOW if two criteria are met. • Task: 1. Apply fixed threshold for DFI vs. FAST comparisons 2. Provide .csv of FAST aerial image + evaluate .src vs. .src difference • Action: .csv format under preparation; .src review pending. • Result: No further meeting required if accepted. • Plan: Final material delivery and customer approval by early June. Awaiting for HQ confirmation.
SEC | AIMS EUV | AIMS EUV 1.0 (Lee, SoonYoung) (Cho, KiWon) | Mask Alignment Failure | * Status: AIMS EUV 1.0 mask alignment failure observed * Task :Investigate AIMS EUV 1.0 alignment failure * Action: - POA applicable after improving VIS–EUV offset setting description - increase spiral search counts in VIS and EUV alignment | Required to check logs to trace spiral searches | April
SEC | AIMS EUV | AIMS EUV 3.0 (P4) (Lee, SoonYoung) (Cho, KiWon) | Sigma Aperture Load/Unload Analysis | * Status: Sigma Aperture Load/Unload failed, Bert went to FATAL * Task : Analyze the dynamics of M1 and Bertrand to determine if the DQ (Dynamic Qualification) is still acceptable. * Action: 1) Request support from Hunn to perform specific measurements using the POBTool, following the guidelines from "PID 4378 COM OMC Dynamic Qualification." 2) The tests involve various configurations of M1 and Bertrand, including standstill and frequency response function (FRF) measurements. 3) DQ measurement for Bert taken on Nov 14th * Result: The support and results will provide solutions to the current state of the DQ for both M1 and Bertrand. Waiting actions from HQ (Patrick, Marat) | Service task during DFI upgrade (2026.03.17) | 3_20 | - Status: No communication to CCD after firmware rollback - AT(Acceptance Test) after CCD camera replacement - Task : To run short AT after CCD replacement since it has entered the vacuum chamber that impacts measurement. - Action: 13 hours of AT items will be conducted on Nov, 6~7. [Estimated completion: CW45] - Result: Satisfy previous AT spec target.
SEC | AIMS EUV (Advanced) | AIMS EUV | NDA Document for Phase Metrology and WLCD | * Status: Getting NDA for Phase Metrology & WLCD EUV * Task: precise measurement using Aerial Image * Action: SEC expect to have AIMS EUV raw data available - SEC have ability to have resist modeling | * Plan: 1. Setup call with SEC and HQ after easter holiday (Dr. Roh)
SEC | AIMS EUV | AIMS EUV 3.0 (Lee, SoonYoung) | Defect numbering mismatch | * Status: Defect numbering mismatch * Task: to fix Defect numbering mismatch in rff file * Action: Investigation required. Figured out root cause file (pos vs RFF) * Result: problematic rff files will be shared among with logs once re-occurrence. | * Plan: will receive further data once reoccurred. | 3_30
SEC | AIMS EUV | AAA EUV 3.0 (KiWon Cho) | High NA evaluation | * Status: Customer requests High NA evaluation setting * Task: correlating with “High NA strange FoV” issue above | * Current satus for FF4. item gathereing. Plan to be shared in the middle of April. | 3_30
SEC | AIMS EUV | AIMS EUV 3.0 (KiWon Cho) | High NA strange FoV | * Status: 90 deg Mask alignment setting is a possible cause * Task: root cause analysis done * Action: Found the root-cause To be rolled out (FF4 expected) | Waiting for the FF4 release | 3_30
SEC | AIMS DUV | AIMS 1x (NRD) (WonTae) | AIMS 1x SW Upgrade to Version 6.18.3 | * Status: AIMS 1x 6.18.3 SW need to be upgrade. Cause 6.15 have an issue with init too long. * Action: S/W upgraded 6.12 to 6.15. found init took so long. * Result: HQ have shared new Database file. Ready to upgrade | * Plan: Upgrade Tool S/W Ver 6.18.3 (Current: 6.12). (ETA) - AIMS 1x SRD : Post Quarterly PM (PM date 4.13-4.15) - AIMS 1x SR1 : Aligning date | 04_06
SEC | AAA | AAA (FAVOR P4) (Kim, WonTae) | AAA SW Upgrade | * Status: AAA 2.34 upgrade (Current: 2.33) (Target :2.34) * Task : AAA SW 2.34 upgrade * Action: Customer have installed AAA 2.34.1 to DUV VM & EUV VM of FAVOR 3.1 in DataCenter | * Plan: Delayed due to AIMS EUV C2 Down. Will be implemented once AIMS EUV C2 UP | 04_06
SEC | AAA | AAA (FAVOR) (Kim, WonTae) | P2 FAVOR 3.1 connection | * Status: Switching the FAVOR Server connections (From NRD to P2 Data-Center: FAVOR 3.1) * Task : Change AAA Server for Tools (2 x AIMS-1x, AIMS FabNeo, AIMS EUV 1.0) * Action: N/A | * Plan: Delayed due to AIMS EUV C2 Down. Will be implemented once AIMS EUV C2 UP | 04_06
SEC | AAA | AAA FAVOR (P4) (WonTae) | AAA Defect Numbering Identification | * Status: P4 AAA, defect numbering in RNR jobs * Action: confirming different defect numbering logic depending on Position job format (POS vs. RFF). * Result: Defect-level comparison, tracking, and automated analysis are not feasible in P4 AAA RNR results, | * Plan : Awaiting until AIMS EUV roll out the New S/W with feature (Root Cause: AIMS EUV S/W) | 3_23
SEC | AAA | AAA FAVOR(P4) (WonTae) | FAVOR 3.0 Multiple Process Error Investigation | * Status: P4 FAVOR 3.0 Multiple Process Error * Action: No problem with running single process. * Result: Customer shared Log files from AAA. The log files were uploaded FTP | *Plan : HQ will release New SW ver with fixed the bug. Target Version is 2.36 (Current ver 2.34) | 04_06
SEC | Tuning | ForTune MLM (HyeRim) | SECS GEM 300 Application Automation Preparation | * Situation: SECS GEM 300 Application part * Task : Job creation automation preparation * Action: Discuss FTM workflow with HQ and customer (March 18th) | • Plan: HQ Check if customer requirement for FTM is applicable (Target date : e/o May) Requirement: To use Normalized R drop Option for mesh size 50, 100 and 200um Etc. | 3_23 | #VALUE!
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with Demo Tool | * Situation: Full fields demo – Feb with demo tool * Task : Full fields demo with demo tool on Feb (Schedule : TBD) * Action: Export license approval is completed | • Plan: Ship the mask to HQ once the export is available (Target date : Once airspace has been opened due to geopolitical issue) | 3_23
SEC | Tuning | ForTune MLM (HyeRim) | Full Fields Demo with HVM Tool | * Situation: Full fields demos (2 demos) – Mar with HVM tool * Task : Two Full fields demo on Mar with alpha or beta tool * Action: Share the information that the demo might available on May | • Plan: Perform the demo on May
SEC | Tuning | ForTune MLM (HyeRim) | Blank 5 Mask Process Completion | * Situation: Blank 5 mask process (Redo EUV CDC after RegC) * Task : HQ perform the process RegC and EUV CDC both at HQ side * Action: EUVR data was shared by customer. Under analysis at HQ side --> Not clear rootcuase found. The big susepct is interference | • Plan: Evaluate HVM tool base DOE (Samsung will share new DOE) by end of April | 04_06
SEC | Tuning | ForTune MLM (HyeRim) | Customer Visit to HQ for Technical Discussion | * Situation: Customer visit to HQ for technical discussion and tool review * Task : Align the schedule and agenda of customer visit * Action: Discuss with HQ about schedule and agenda | • Plan: Have the available schedule from HQ + Have the agenda from customer(expected date : TBD)
SEC | Tuning | ForTune MLM (HyeRim) | Blank 6 Mask Process Report Preparation | * Status: Blank 6 mask process (2nd RegC after EUV CDC) - (CW03) * Task : Perform 2nd RegC after EUV CDC at Samsung side * Action: Customer shared EUVR and registration data | * Plan: HQ prepare the report (Scheduled : TBD) (Priority: Low)
SEC | Tuning | ForTune MLM (HyeRim) | PIP Roughness Measurement on Blank 1 & 2 | * Status: PIP on blank 1&2 roughness measurement * Task : Roughness measurement on blank 1&2 to check difference PW tendency on blank 1&2 * Action: ZEISS suggest to perform this item once HVM tool is ready  Samsung accept it | * Plan: Wait for HVM tool (alpha or beta) (Rought timeline: After May)
SEC | Tuning | ForTune DUV (HyeRim) | Fortune DUV SECS GEM 300 Scenario Discussion | * Status: Fortune DUV SECS GEM 300 Scenario discussion (CDC) - (Priority: Low) * Task : Share automation information in case .dat file cause errors. * Action:ZEISS shared the information Samsung asked (e.g ALID, S16F12 ACKA) --> Samsung request addtional thing (Stop status instead of Abort) | * Plan: - Have HQ feedback for additional Samsung requirement Samsung wants have the “Stop” button instead of “Aborted” when wrong format of the DAT file loaded. | 04_06
SEC | Tuning | ForTune DUV (HyeRim) (DongHoon Koo) | Fortune DUV SW Upgrade Connection Issue | * Status: Fortune DUV SW upgrade 5.9.3 – FTM connection failure (Priority: Low) * Task : To clear FTM connection failure during SW 5.9.3 initialization * Action: Perform action item (to check if port is open properly) by HQ on Jan 28th and shared ForTuneReleaseInfo.txt file | * Plan: Postpone resolving the issue for now since full automation is not yet supported. After installing F312 and completing the full automation tests there, we will upgrade F306 to the same version and address this issue if it still persists
SEC | Tuning | ForTune EUV (Ji HyeRim) | Pixel Non-uniformity Investigation | * Status: Pixel non uniformity (Low-Light) * Task : To figure out why there is pixel non uniformity phenomena at E601(SR1) & E605 (P4) * Action: Samsung share the results of BYSTRIPE method | * Plan: HQ share slides which include root cause of pixel non uniformity by week of Nov 3rd (Schedule for sharing the slides delayed with other priority topics, schedule is not fixed)
SEC | Tuning | ForTune EUV (Ji HyeRim) | Mask Thickness Deviation Analysis | * Status: Mask thickness deviation between E601(SR1)&E605(P4) (Low-Light) * Task : To match z height deviation between tools (as Samsung uses the absolute number for map distance, mask thickness value is not relevant) * Action: Samsung measured pixel images on May 2025 and shared it to ZEISS last week * Result: Need a further action. | * Plan: ZEISS look into the result
SEC | Tuning | ForTune DUV (F 312) (Ji HyeRim) | ForTune DUV #2 SECS GEM 300 2D Job Support Discussion | * Situation: ForTune DUV #2 (F312) SECS GEM 300 support 2D jobs * Task : Need to test 2D jobs with the tool * Action: Ask to customer to share real measurement result on the simulation files that customer shared last year to compare 2D and 3D result | • Plan : HQ will test SECS GEM at HQ tool to check if 2D job is supported or not + ZEISS compare 3D and 2D results to convince customer to use 3D jobs even 2D job works (Target date : m/o April) | 3_30
SEC | Tuning | ForTune EUV | High Resolution RegC Demo | * Situation: High resolution RegC demo (2026-02-23) * Task : Perform high resolution RegC demo and share relevant files (job files and induced files) * Action: Samsung shared required files | • Plan : Share simulation results from HQ by end of April | 04_06
SEC | PROVE | PROVE neXT (SR1) | LRM feature enablement (FAVOR) (Priority: High) | * Status: Customer inquired about the possibility of using the LRM function * Task :HQ confirmed that FAVOR 3.0 need to be fixed to enable LRM feature * Action: Investigate FAVOR3.0 with HQ engineers (2026-Mar-06) * Result: FAVOR3.0 seems fine, but PROVE still couldn't connect to FAVOR3.0. Need a PROVE FoB Help | * Plan: Discuss with HQ regarding PROVE connection Help Need: Need a support plan from PROVE FoB Ticket: https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=785216 | (Priority: High) | * link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=785216"
SEC | PROVE | PROVE | In-cell measurement out of spec (Priority: High) | Status: Analyze if correlation mode cause registration offset Action: Conference call with stakeholders ( HQ, SEC , Local ) has been made. We will conduct more information from samsung to achieve their internal requirement regarding incell measurement Result: Request incell accuracy measurement | * Waiting for Incell accuracy result from customer - ETA: by April, awaiting since Feb 2026. * In parallel, SSC will conduct more information during additional customer meeting ( Customer meeting will be held at CW15 ) | 04_06 | * Link: "https://tfs.zeiss.org/tfs/SMT_SMS/PROVE/_backlogs/backlog/PROVE-Application%20KR/Stories/?workitem=778865"
SEC | PROVE | PROVE | TTTM transition from HR to neXT | * Status: The customer is currently using PROVE HR as the Master tool for TTTM. * Task: Transfer Master tool from PROVE HR to PROVE neXT. * Action: The customer will make new “Grid Mask” to tune the PROVE neXT. * Result: The introduction of the new grid mask has been temporarily put on hold. | Monitor the progress of the master tool transition.
SEC | PROVE | PROVE | High-Performance mode demo | Status: Customer want to evaluate HPM demo’s resolution Action: Align tool time for demo measurement Result: Demo mask has been sent to HQ | * Demo Mask shipped out: 3rd April to Jena * Tool-time in HQ: end of May ( Still under discussion ) | 04_06
SEC | PROVE | PROVE HR (NRD) | Hang-up issue during measurement | * Status: Customer repeatedly asked about the ongoing hang-up issue * Action: Reported the issue to HQ and requested additional action items. * Result: No resolution yet. The customer is waiting for an update | Request HQ to escalate the priority and provide a concrete action plan as soon as possible. No progress since 2025 | 04_06
SEC | PROVE | PROVE | SW feature request - Offline re-measurement | * Status: Customer requested new SW feature * Action: Created SW feature request ticket to escalate to HQ * Result: - | Waiting for HQ feedback ( Target : 2026 May ) No progress since CW13 | 04_06
SK hynix | Repair | LE #2 (Plan) | Source Inspection | * Status: Source inspection on 18th May ~ 20nd May 2026 * Task: Preparation of Source inspection. * Action: Customer visiting has been canceled. | * HQ Source report need to be provided to SKH before 18th May
| Repair | LE #2 (Plan) | NOCl only recipe request | * Status: NOCl only shape request for particle removal. * Task: Align with HQ for providing NOCl only recipe. * Action: It will be discussed during ATP | * It will be discussed during ATP.
SK hynix | Repair | Auto Repair (with neXT & LE) | Auto Repair 3.0 Evaluation | [Auto Repair 3.0 evaluation on neXT] * Status: Auto Repair evolution on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Auto Repair evaluation on 200 number of production defect until end of March 2026 [Auto Repair 3.0 evaluation on LE] * Status: Auto Repair evaluation on neXT (license : end of June 2026) * Task: Active success rate over 70% on production defect. * Action: Defect centering error has been solved [Auto Repair SimOp evaluation] * Status: Auto Repair SimOp evaluation on neXT & LE (license : end of June 2026) * Task: SimOp Installation * Action: ARC license update in FAVOR. | [Auto Repair 3.0 evaluation on neXT] * Auto Repair evaluation support until March (SangIk & DongHwi / Target : end of March) [Auto Repair 3.0 evaluation on LE] * Auto Repair evaluation support. (SangIk & DongHwi / Target : end of 2026) [Auto Repair SimOp evaluation] * Trouble shooting and set-up (SangIk & DongHwi / Target : end of June)
SK hynix | Repair | Tool Monitoring (with LE) | Tool-monitoring Demo (Sentinel & Datacenter) | * Status : Tool-monitoring Demo evaluation will be discussed after complete Auto Repair Demo evaluation. * Task : Online demo and live evaluation on customer tool. * Action : (1) If customer satisfy online demo then move to live evaluation on tool. (2) HQ on-site Demo in SKH. | * Planning for HQ expert visiting for Tool-monitoring live demo. (David & TaeHoon / Target : Week of May 11) | 3_30
SK hynix | Repair | EUV PSM Process | EUV PSM | [EUV PSM (Ru based)] * Status : EUV PSM under cut issue * Task : Resolve under cut issue with Cl based chemistry. * Action : HQ update is needed [EUV PSM High-NA (Pt based)] * Status : Abs. materials is fixed as RuPt, SKH will decide materials for buffer layer. Target : 2028 for Mask / 2029 for wafer. * Task : Open discussion with SKH for buffer layer candidate - Candidate : CrN / no buffer * Action : HQ will provide additional data what customer request. | [EUV PSM (Ru based)] * HQ will provide status update - Felix / Target : TBD [EUV PSM High-NA (Pt based)] * Cap layer selectivity test with exist and new chemistry - Felix & SKH / Target : TBD. | 3_23
SK hynix | AIMS EUV | FAVOR 3.1 (KiWon, Cho) | SSD Storage Expansion for AIMS EUV | * Status: SK hynix request to have more storage for AIMS EUV into FAVOR. * Task : Procure SSD storage through Local order via NTT Korea (Cross-charge approval: Confirmed by Menno) * Action: 1) Budgetary for 6 SSD cards forwarded to HQ and awaiting confirmation (2025-12-29) * Result: N/A | Scheduling in May | May | * FAVOR 3.1 Data storage: 10TB availability
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | AE3 Mask Alignment Redefinition | * Status: AE3 mask align redefine. * Task : To set corrective actions for MA. * Action: Will act on FF2 upgrade * Result: MA align redefine completed. * Customer mask for align1&2 defined. No spiral search | * H/W action need to be done (Stage Jump), estimated in April. - Ticket transferred to Service from Apps. | 3_30
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Threshold/CD fluctuation | Ticket: https://tfs.zeiss.org/tfs/SMT_SMS/AIMS-EUV/_workitems/edit/851452 Status : AAA Analysis Task : Evaluate of RST jump is required on-site (RST: Retile Stage) | • Plan : verify tool performance once done H/W action below. HQ service prepares PoA to check. Then local team will follow up onsite. 2026-04-06 No update from HQ so far | 04_06
SK hynix | AIMS EUV | AIMS EUV 3.0 (KiWon) | Slow DFI algorithm issue | * Status : Found the issue at inactive GPU * Task : Restart #2/ #3 Server during next bore swap. * FYI : Fan-noise happened at server #1 | • Restart FAVOR servers during next bore swap. (2026-04-06 : 10 h remaining) | 04_06
SK hynix | AAA EUV AIMS EUV | AAA EUV AIMS EUV 3.0 (WonTae) (KiWon) | Separation of license Dongle | * Status: Separation License dongle in SW AAA client & EUV batch Editor * Action: Escalated it to HQ. Requested Physical Dongle to separate them * Result: need discussion with HQ | * Plan : customer meeting with HQ on April 8th. - plan to reproduce current situation via online meeting. | 04_06
SK hynix | AIMS DUV | AIMS fab neo (WonTae) | Low intensity with New Lamp (Hamamatsu) | * Status: Hamamatsu lamp has low intensity. Customer request Lamp replacement & ATP * Action: Replaced the lamp and Done ATP measurement in March * Result: Due to intensity low, New lamp replacement is needed on April. | * Plan : Next Lamp replacement date : 4.30 - 4.31 | 3_23
SK hynix | AIMS DUV | AIMS 1x (WonTae) | AIMS 1x TTTM Defect Size Measurement Discussion | * Status: Defined the Gap between SK hynix and ZEISS with AIMS 1x TTTM Specification. * Action: HQ & SK Hynix had discussion for this topic in CW10 * Result: H/W action involved. (Beam alignment. Disar intensity is uniform) in b/o March | * Plan : Will have a customer meeting with HQ on April 8th. - Discussion with Specification gap | 04_06
SK hynix | AIMS DUV | WLCD (WonTae) | WLCD Measurement for BACUS 2026 Publication | * Status: DUV WLCD Measurement for BACUS 2026 publication * Action: align measurement files. Cleaning Tool is in production. Waiting for Job Schedule. * Result: No internal draft until 23rd of April | * Plan : HQ will share DUV WLCD strategy after Germany Easter Holiday | 3_30
SK hynix | Tuning | ForTune EUV (HyeRim) | Additional Demo with SNM Mask | * Status: Additional demo with SNM mask * Task : Demo with SNM mask to see if 2 corrected masks show better overlay improvement * Action: Post registration and overlay data was shared | * Plan: HQ analyze the data if overlay has been improved (Target date : e/o April) | 3_23 | [Previous] 2) SPICA (Correction) demo: Wafer printing result expected to be shared by this week. * LUCY [D1b], SPICA [D1c]
SK hynix | PROVE | PROVE neXT (KiWon) | Measurement feasibility demo ( Box/Stamp mode ) | * Status: Check if the current tech(LUCY) patterns can be measured with PROVE neXT (SK Hynix shared the DB file) * Task : Check the DB file theoretically + Conduct simulation with the DB file to check if the tool is able to resolve the patterns * Action: Clip file for box mode demo has been delivered to HQ to proceed additional demo measurement. * Result: Waiting for HQ to provide the demo measurement results. | * Demo result shared to customerl customer evaluation to follow. * No update this week due to German holidays | 04_06
SK hynix | PROVE | PROVE neXT (DongHoon) | SW requirement for Production | * Status: A customer has inquired to have desired feature in PROVE. * Action : Customer requested several feature request to integrates PROVE SW into their automated workflow. * Result: Created multiple ticket to escalate to HQ regarding SW feature that customer requested. | * Customer requests will be reflected in the HQ SW release (target: Dec 2026). * No progress since CW13 | 04_06
SK hynix | PROVE | PROVE neXT (KiWon) | EUV mask requirement for ATP | * Status : Need HQ help for further support for EUV mask fabrifaction for ATP. * Task : three question below. * Action: 1) Need to be removed the L0 layer, which is currently applied as an overall layer. 2) Justification is required explaining for reverse tonality to the pattern. 3) Need a confirmation for the clear field indication, is reverse tonality required. | * Awaiting HQ feedback. for 2) Justitication of reverse tonality by customer's request (Low priority) * SKH started the mask production * Plan to ship customer mask to HQ ( Target : 2026 May ) | 04_06
Tekscend | Repair | MG neo ( M141) (TaekKyoung) | Application ATP | * Status: F-ATP completion on 22nd Jan (Signed off 10th March) * Task :Pending items discussion * Action: HQ process support is needed, if issue happens on production. | * Waiting for customer feedback for potential process issue on production. | 3_16